## Slide 1: Advancing the Medicaid IT Enterprise Project
Reference Architecture Update – August 11, 2017
CMS ALLIANCE TO MODERNIZE HEALTHCARE

## Slide 2: Agenda
Poplin Working Group Update
Domain-specific service definition schedules

## Slide 3: Poplin Working Group
Last Two Weeks
  MESC results
    Preconference session on Poplin was well-received and generated vigorous discussion
    Added WV, NM, and WY to states wanting to participate in Poplin WG. CA also expressed interest in returning.
    Deloitte, Oracle, and WiPro also expressed interest in Poplin
    Followed up with MESC contacts
  Received overall schedule from CNSI
  Vermont presented detailed business process work on Case Management functional area which was well-received
  Presented Poplin to MITA-TAC
  Scheduled Poplin presentations to MTA and HSI-TAG the week of September 18th.
This week
  First drafts of service definitions for registration / discovery and messaging shared services
  Continued work on service definitions by Poplin WG members
  Poplin Overview Article for MES Newsletter

## Slide 4: Domain-specific Service Definition Schedules
Vermont
Task | Status | Assigned To | LOE SWAG (S/M/L/XL) | Due Date | Comments/Notes | Sprint count
Case Management Service Definition |  |  |  |  |  | 
Client/Member Management |  |  |  | 12/1/17 |  | 
Process definitions - Process flow diagrams, Process descriptions (UML) | Not Started | CJ, Tim, Andrew | L | 10/20/17 | 7 high-level processes in MM | 2
Object definitions - Context, class, interaction, ER diagrams (UML / SysML) | Not Started | CJ, Tim, Andrew | L | 11/3/17 |  | 3
Resource definitions - Sample resource template with required fields | Not Started | CJ, Tim, Andrew | M | 11/27/17 |  | 1
API Specification - Sample API spec with required fields | Not Started | CJ, Tim, Andrew | M | 11/27/17 |  | 1
Service Management | In Progress |  |  | 10/1/17 |  | 
Process definitions - Process flow diagrams, Process descriptions (UML) | In Progress | CJ, Tim, Andrew | XL | 8/25/17 | 19 high-level processes in Care Management. 1 high-level process in Operations Management. Several interactions with other areas. | 2
Object definitions - Context, class, interaction, ER diagrams (UML / SysML) | In Progress | CJ, Tim, Andrew | XL | 9/8/17 |  | 2
Resource definitions - Sample resource template with required fields | Not Started | CJ, Tim, Andrew | L | 9/15/17 |  | 3
API Specification - Sample API spec with required fields | Not Started | CJ, Tim, Andrew | L | 9/22/17 |  | 1
Eligibility & Enrollment |  |  |  | 12/1/17 | 5 high-level processes | 
Process definitions - Process flow diagrams, Process descriptions (UML) | Not Started | CJ, Tim, Andrew | XL | 10/20/17 |  | 2
Object definitions - Context, class, interaction, ER diagrams (UML / SysML) | Not Started | CJ, Tim, Andrew | XL | 11/3/17 |  | 3
Resource definitions - Sample resource template with required fields | Not Started | CJ, Tim, Andrew | L | 11/27/17 |  | 1
API Specification - Sample API spec with required fields | Not Started | CJ, Tim, Andrew | L | 11/27/17 |  | 1

## Slide 5: Domain-specific Service Definition Schedules
CNSI
Epic # | Epic Name | Deliverable | Draft Version Release Date | Final Version Release Date
RA-PE - EE05 -01 | EE05:DetermineProviderEligibility - Activity Information Flow | Process Flow (Activity) | 9/29/2017 | 10/13/2017
RA-PE - EE05 -02 | EE05:DetermineProviderEligibility - Functional Decomposition of Performer | Process Flow (Functions) | 11/3/2017 | 11/17/2017
RA-PE - EE05 -03 | EE05:DetermineProviderEligibility - Resource Decomposition | Object/Resource Definition | 12/1/2017 | 12/15/2017
RA-PE - EE05 -04 | EE05:DetermineProviderEligibility - Service Specification | API Specification | 12/15/2017 | 12/29/2017
RA-PE - EE06 -01 | EE06:EnrollProvider - Activity Information Flow | Process Flow (Activity) | 10/6/2017 | 10/20/2017
RA-PE - EE06 -02 | EE06:EnrollProvider - Functional Decomposition of Performer | Process Flow (Functions) | 11/10/2017 | 11/24/2017
RA-PE - EE06 -03 | EE06:EnrollProvider - Resource Decomposition | Object/Resource Definition | 12/8/2017 | 12/22/2017
RA-PE - EE06 -04 | EE06:EnrollProvider - Service Specification | API Specification | 12/22/2017 | 1/5/2018
RA-PE - EE07 -01 | EE07:DisenrollProvider - Activity Information Flow | Process Flow (Activity) | 10/13/2017 | 10/27/2017
RA-PE - EE07 -02 | EE07:DisenrollProvider - Functional Decomposition of Performer | Process Flow (Functions) | 11/17/2017 | 12/1/2017
RA-PE - EE07 -03 | EE07:DisenrollProvider - Resource Decomposition | Object/Resource Definition | 12/15/2017 | 12/29/2017
RA-PE - EE07 -04 | EE07:DisenrollProvider - Service Specification | API Specification | 12/29/2017 | 1/12/2018
RA-PE - EE08 -01 | EE08:InquireProviderInformation - Activity Information Flow | Process Flow (Activity) | 10/20/2017 | 11/3/2017
RA-PE - EE08 -02 | EE08:InquireProviderInformation - Functional Decomposition of Performer | Process Flow (Functions) | 11/24/2017 | 12/8/2017
RA-PE - EE08 -03 | EE08:InquireProviderInformation - Resource Decomposition | Object/Resource Definition | 12/22/2017 | 1/5/2018
RA-PE - EE08 -04 | EE08:InquireProviderInformation - Service Specification | API Specification | 1/5/2018 | 1/19/2018
RA-PM- PM01 -01 | PM01:ManageProviderInformation - Activity Information Flow | Process Flow (Activity) | 12/29/2017 | 1/12/2018
RA-PM- PM01 -02 | PM01:ManageProviderInformation - Functional Decomposition of Performer | Process Flow (Functions) | 1/19/2018 | 2/2/2018
RA-PM- PM01 -03 | PM01:ManageProviderInformation - Resource Decomposition | Object/Resource Definition | 2/2/2018 | 2/16/2018
RA-PM- PM01 -04 | PM01:ManageProviderInformation - Service Specification | API Specification | 2/16/2018 | 3/2/2018

## Slide 6: Domain-specific Service Definition Schedules
CNSI (continued)
Epic # | Epic Name | Deliverable | Draft Version Release Date | Final Version Release Date
RA-PM- PM02 -01 | PM02:ManageProviderCommunication - Activity Information Flow | Process Flow (Activity) | 1/5/2018 | 1/19/2018
RA-PM- PM02 -02 | PM02:ManageProviderCommunication - Functional Decomposition of Performer | Process Flow (Functions) | 1/26/2018 | 2/9/2018
RA-PM- PM02 -03 | PM02:ManageProviderCommunication - Resource Decomposition | Object/Resource Definition | 2/9/2018 | 2/23/2018
RA-PM- PM02 -04 | PM02:ManageProviderCommunication - Service Specification | API Specification | 2/23/2018 | 3/9/2018
RA-PM- PM03 -01 | PM03:PerformProviderOutreach - Activity Information Flow | Process Flow (Activity) | 1/12/2018 | 1/26/2018
RA-PM- PM03 -02 | PM03:PerformProviderOutreach - Functional Decomposition of Performer | Process Flow (Functions) | 2/2/2018 | 2/16/2018
RA-PM- PM03 -03 | PM03:PerformProviderOutreach - Resource Decomposition | Object/Resource Definition | 2/16/2018 | 3/2/2018
RA-PM- PM03 -04 | PM03:PerformProviderOutreach - Service Specification | API Specification | 3/2/2018 | 3/16/2018
RA-PM- PM07 -01 | PM07:ManageProviderGrievanceAndAppeal - Activity Information Flow | Process Flow (Activity) | 1/19/2018 | 2/2/2018
RA-PM- PM07 -02 | PM07:ManageProviderGrievanceAndAppeal - Functional Decomposition of Performer | Process Flow (Functions) | 2/9/2018 | 2/23/2018
RA-PM- PM07 -03 | PM07:ManageProviderGrievanceAndAppeal - Resource Decomposition | Object/Resource Definition | 2/23/2018 | 3/9/2018
RA-PM- PM07 -04 | PM07:ManageProviderGrievanceAndAppeal - Service Specification | API Specification | 3/9/2018 | 3/23/2018
RA-PM- PM08 -01 | PM08:TerminateProvider - Activity Information Flow | Process Flow (Activity) | 1/26/2018 | 2/9/2018
RA-PM- PM08 -02 | PM08:TerminateProvider - Functional Decomposition of Performer | Process Flow (Functions) | 2/16/2018 | 3/2/2018
RA-PM- PM08 -03 | PM08:TerminateProvider - Resource Decomposition | Object/Resource Definition | 3/2/2018 | 3/16/2018
RA-PM- PM08 -04 | PM08:TerminateProvider - Service Specification | API Specification | 3/16/2018 | 3/30/2018