## Slide 1: Advancing the Medicaid IT Enterprise Project
Reference Architecture Update – August 11, 2017
CMS ALLIANCE TO MODERNIZE HEALTHCARE

## Slide 2: Agenda
Poplin Working Group Updates

## Slide 3: Poplin Working Group
Last Week
  New members
    WY and NM joined the call
    MESC results
  HIT Connect Meeting (April 5-6 in Baltimore)
    Abstract due at the end of the month
    Drafted abstract
  CNSI is working on Provider Eligibility Process Flow Diagram and adding another member to the team
  MITRE continues to work on message and service registration and discovery service definitions
    Covered potential solutions for message and service registration and discovery, pros and cons
  Vermont is progressing on schedule with service definition development, object definition for case management (mid-sprint), extended toward ERDs and context diagrams
  Drafted Poplin Overview Article for MES Newsletter
This week
  Reaching out to new members to define their interest in functional areas
  First drafts of service definitions for registration / discovery and messaging shared services
  Continued work on service definitions by Poplin WG members

## Slide 4: Domain-specific Service Definition Schedules
Vermont
Task | Status | Assigned To | LOE SWAG (S/M/L/XL) | Due Date | Comments/Notes | Sprint count
Case Management Service Definition |  |  |  |  |  | 
Client/Member Management |  |  |  | 12/1/17 |  | 
Process definitions - Process flow diagrams, Process descriptions (UML) | Not Started | CJ, Tim, Andrew | L | 10/20/17 | 7 high-level processes in MM | 2
Object definitions - Context, class, interaction, ER diagrams (UML / SysML) | Not Started | CJ, Tim, Andrew | L | 11/3/17 |  | 3
Resource definitions - Sample resource template with required fields | Not Started | CJ, Tim, Andrew | M | 11/27/17 |  | 1
API Specification - Sample API spec with required fields | Not Started | CJ, Tim, Andrew | M | 11/27/17 |  | 1
Service Management | In Progress |  |  | 10/1/17 |  | 
Process definitions - Process flow diagrams, Process descriptions (UML) | In Progress | CJ, Tim, Andrew | XL | 8/25/17 | 19 high-level processes in Care Management. 1 high-level process in Operations Management. Several interactions with other areas. | 2
Object definitions - Context, class, interaction, ER diagrams (UML / SysML) | In Progress | CJ, Tim, Andrew | XL | 9/8/17 |  | 2
Resource definitions - Sample resource template with required fields | Not Started | CJ, Tim, Andrew | L | 9/15/17 |  | 3
API Specification - Sample API spec with required fields | Not Started | CJ, Tim, Andrew | L | 9/22/17 |  | 1
Eligibility & Enrollment |  |  |  | 12/1/17 | 5 high-level processes | 
Process definitions - Process flow diagrams, Process descriptions (UML) | Not Started | CJ, Tim, Andrew | XL | 10/20/17 |  | 2
Object definitions - Context, class, interaction, ER diagrams (UML / SysML) | Not Started | CJ, Tim, Andrew | XL | 11/3/17 |  | 3
Resource definitions - Sample resource template with required fields | Not Started | CJ, Tim, Andrew | L | 11/27/17 |  | 1
API Specification - Sample API spec with required fields | Not Started | CJ, Tim, Andrew | L | 11/27/17 |  | 1

## Slide 5: Domain-specific Service Definition Schedules
CNSI
Epic # | Epic Name | Deliverable | Draft Version Release Date | Final Version Release Date
RA-PE - EE05 -01 | EE05:DetermineProviderEligibility - Activity Information Flow | Process Flow (Activity) | 9/29/2017 | 10/13/2017
RA-PE - EE05 -02 | EE05:DetermineProviderEligibility - Functional Decomposition of Performer | Process Flow (Functions) | 11/3/2017 | 11/17/2017
RA-PE - EE05 -03 | EE05:DetermineProviderEligibility - Resource Decomposition | Object/Resource Definition | 12/1/2017 | 12/15/2017
RA-PE - EE05 -04 | EE05:DetermineProviderEligibility - Service Specification | API Specification | 12/15/2017 | 12/29/2017
RA-PE - EE06 -01 | EE06:EnrollProvider - Activity Information Flow | Process Flow (Activity) | 10/6/2017 | 10/20/2017
RA-PE - EE06 -02 | EE06:EnrollProvider - Functional Decomposition of Performer | Process Flow (Functions) | 11/10/2017 | 11/24/2017
RA-PE - EE06 -03 | EE06:EnrollProvider - Resource Decomposition | Object/Resource Definition | 12/8/2017 | 12/22/2017
RA-PE - EE06 -04 | EE06:EnrollProvider - Service Specification | API Specification | 12/22/2017 | 1/5/2018
RA-PE - EE07 -01 | EE07:DisenrollProvider - Activity Information Flow | Process Flow (Activity) | 10/13/2017 | 10/27/2017
RA-PE - EE07 -02 | EE07:DisenrollProvider - Functional Decomposition of Performer | Process Flow (Functions) | 11/17/2017 | 12/1/2017
RA-PE - EE07 -03 | EE07:DisenrollProvider - Resource Decomposition | Object/Resource Definition | 12/15/2017 | 12/29/2017
RA-PE - EE07 -04 | EE07:DisenrollProvider - Service Specification | API Specification | 12/29/2017 | 1/12/2018
RA-PE - EE08 -01 | EE08:InquireProviderInformation - Activity Information Flow | Process Flow (Activity) | 10/20/2017 | 11/3/2017
RA-PE - EE08 -02 | EE08:InquireProviderInformation - Functional Decomposition of Performer | Process Flow (Functions) | 11/24/2017 | 12/8/2017
RA-PE - EE08 -03 | EE08:InquireProviderInformation - Resource Decomposition | Object/Resource Definition | 12/22/2017 | 1/5/2018
RA-PE - EE08 -04 | EE08:InquireProviderInformation - Service Specification | API Specification | 1/5/2018 | 1/19/2018
RA-PM- PM01 -01 | PM01:ManageProviderInformation - Activity Information Flow | Process Flow (Activity) | 12/29/2017 | 1/12/2018
RA-PM- PM01 -02 | PM01:ManageProviderInformation - Functional Decomposition of Performer | Process Flow (Functions) | 1/19/2018 | 2/2/2018
RA-PM- PM01 -03 | PM01:ManageProviderInformation - Resource Decomposition | Object/Resource Definition | 2/2/2018 | 2/16/2018
RA-PM- PM01 -04 | PM01:ManageProviderInformation - Service Specification | API Specification | 2/16/2018 | 3/2/2018

## Slide 6: Domain-specific Service Definition Schedules
CNSI (continued)
Epic # | Epic Name | Deliverable | Draft Version Release Date | Final Version Release Date
RA-PM- PM02 -01 | PM02:ManageProviderCommunication - Activity Information Flow | Process Flow (Activity) | 1/5/2018 | 1/19/2018
RA-PM- PM02 -02 | PM02:ManageProviderCommunication - Functional Decomposition of Performer | Process Flow (Functions) | 1/26/2018 | 2/9/2018
RA-PM- PM02 -03 | PM02:ManageProviderCommunication - Resource Decomposition | Object/Resource Definition | 2/9/2018 | 2/23/2018
RA-PM- PM02 -04 | PM02:ManageProviderCommunication - Service Specification | API Specification | 2/23/2018 | 3/9/2018
RA-PM- PM03 -01 | PM03:PerformProviderOutreach - Activity Information Flow | Process Flow (Activity) | 1/12/2018 | 1/26/2018
RA-PM- PM03 -02 | PM03:PerformProviderOutreach - Functional Decomposition of Performer | Process Flow (Functions) | 2/2/2018 | 2/16/2018
RA-PM- PM03 -03 | PM03:PerformProviderOutreach - Resource Decomposition | Object/Resource Definition | 2/16/2018 | 3/2/2018
RA-PM- PM03 -04 | PM03:PerformProviderOutreach - Service Specification | API Specification | 3/2/2018 | 3/16/2018
RA-PM- PM07 -01 | PM07:ManageProviderGrievanceAndAppeal - Activity Information Flow | Process Flow (Activity) | 1/19/2018 | 2/2/2018
RA-PM- PM07 -02 | PM07:ManageProviderGrievanceAndAppeal - Functional Decomposition of Performer | Process Flow (Functions) | 2/9/2018 | 2/23/2018
RA-PM- PM07 -03 | PM07:ManageProviderGrievanceAndAppeal - Resource Decomposition | Object/Resource Definition | 2/23/2018 | 3/9/2018
RA-PM- PM07 -04 | PM07:ManageProviderGrievanceAndAppeal - Service Specification | API Specification | 3/9/2018 | 3/23/2018
RA-PM- PM08 -01 | PM08:TerminateProvider - Activity Information Flow | Process Flow (Activity) | 1/26/2018 | 2/9/2018
RA-PM- PM08 -02 | PM08:TerminateProvider - Functional Decomposition of Performer | Process Flow (Functions) | 2/16/2018 | 3/2/2018
RA-PM- PM08 -03 | PM08:TerminateProvider - Resource Decomposition | Object/Resource Definition | 3/2/2018 | 3/16/2018
RA-PM- PM08 -04 | PM08:TerminateProvider - Service Specification | API Specification | 3/16/2018 | 3/30/2018