## Slide 1: Advancing the Medicaid IT Enterprise Project
Reference Architecture Update – August 11, 2017
CMS ALLIANCE TO MODERNIZE HEALTHCARE

## Slide 2: Agenda
Poplin Working Group Updates
Functional area coverage

## Slide 3: Poplin Working Group
Last Week
  Launched “Poplin Monthly Update” meeting for 2nd tier participants (third Tuesday at 2:30pm)
  MITRE walked group through service registration and discover service definition, based on Kubernetes
  MITRE continues to work on message and service registration and discovery service definitions
    Covered potential solutions for message and service registration and discovery, pros and cons
  West Virginia committed to 1+ FTE, with focus on member eligibility (#1), member enrollment (#2), and case management (#3)
  Held collaboration meeting with MITA-TAC to determine concrete steps on how MITA-TAC can assist Poplin
  Wyoming not able to commit resources to Poplin at this time
This week
  Vermont to present progress on Case Management service definition
  MITRE to present on messaging service definition
  PSM collaboration meeting to address Montana’s open RFP on provider screening
  Present Poplin to MTA (9/19) and HSITAG (9/21)
  NM to define commitment and their interest in functional areas
  Continued work on service definitions by Poplin WG members

## Slide 4: Functional Areas
Provider Management (CNSI #1)
  Screening (MITRE PSM team, VT #2)
  Enrollment
Claims
Pharmacy
Financial Management
Member Management (VT #2, CNSI #2)
  Eligibility (WV #1)
  Enrollment (WV #2)
Third Party Liability
Case Management (VT #1, WV #3)
  Interaction with E&E (VT #3)
Data Warehouse / Business Intelligence / Analytics
Managed Care Enrollment Broker (CNSI #3)
Shared Services (MITRE Poplin team)
  Service registration / discovery, messaging
Resource Commitment:
CNSI: 2 FTE
VT: 1 FTE
MITRE: 1.5 FTE
WV: 1+ FTE
NM: Next week
Functional Area Commitment:
NM: #1, #2, #3 choices? (next week)

## Slide 5: Domain-specific Service Definition Schedules
Vermont
Task | Status | Assigned To | LOE SWAG (S/M/L/XL) | Due Date | Comments/Notes | Sprint count
Case Management Service Definition |  |  |  |  |  | 
Client/Member Management |  |  |  | 12/1/17 |  | 
Process definitions - Process flow diagrams, Process descriptions (UML) | Not Started | CJ, Tim, Andrew | L | 10/20/17 | 7 high-level processes in MM | 2
Object definitions - Context, class, interaction, ER diagrams (UML / SysML) | Not Started | CJ, Tim, Andrew | L | 11/3/17 |  | 3
Resource definitions - Sample resource template with required fields | Not Started | CJ, Tim, Andrew | M | 11/27/17 |  | 1
API Specification - Sample API spec with required fields | Not Started | CJ, Tim, Andrew | M | 11/27/17 |  | 1
Service Management | In Progress |  |  | 10/1/17 |  | 
Process definitions - Process flow diagrams, Process descriptions (UML) | In Progress | CJ, Tim, Andrew | XL | 8/25/17 | 19 high-level processes in Care Management. 1 high-level process in Operations Management. Several interactions with other areas. | 2
Object definitions - Context, class, interaction, ER diagrams (UML / SysML) | In Progress | CJ, Tim, Andrew | XL | 9/8/17 |  | 2
Resource definitions - Sample resource template with required fields | Not Started | CJ, Tim, Andrew | L | 9/15/17 |  | 3
API Specification - Sample API spec with required fields | Not Started | CJ, Tim, Andrew | L | 9/22/17 |  | 1
Eligibility & Enrollment |  |  |  | 12/1/17 | 5 high-level processes | 
Process definitions - Process flow diagrams, Process descriptions (UML) | Not Started | CJ, Tim, Andrew | XL | 10/20/17 |  | 2
Object definitions - Context, class, interaction, ER diagrams (UML / SysML) | Not Started | CJ, Tim, Andrew | XL | 11/3/17 |  | 3
Resource definitions - Sample resource template with required fields | Not Started | CJ, Tim, Andrew | L | 11/27/17 |  | 1
API Specification - Sample API spec with required fields | Not Started | CJ, Tim, Andrew | L | 11/27/17 |  | 1

## Slide 6: Domain-specific Service Definition Schedules
CNSI
Epic # | Epic Name | Deliverable | Draft Version Release Date | Final Version Release Date
RA-PE - EE05 -01 | EE05:DetermineProviderEligibility - Activity Information Flow | Process Flow (Activity) | 9/29/2017 | 10/13/2017
RA-PE - EE05 -02 | EE05:DetermineProviderEligibility - Functional Decomposition of Performer | Process Flow (Functions) | 11/3/2017 | 11/17/2017
RA-PE - EE05 -03 | EE05:DetermineProviderEligibility - Resource Decomposition | Object/Resource Definition | 12/1/2017 | 12/15/2017
RA-PE - EE05 -04 | EE05:DetermineProviderEligibility - Service Specification | API Specification | 12/15/2017 | 12/29/2017
RA-PE - EE06 -01 | EE06:EnrollProvider - Activity Information Flow | Process Flow (Activity) | 10/6/2017 | 10/20/2017
RA-PE - EE06 -02 | EE06:EnrollProvider - Functional Decomposition of Performer | Process Flow (Functions) | 11/10/2017 | 11/24/2017
RA-PE - EE06 -03 | EE06:EnrollProvider - Resource Decomposition | Object/Resource Definition | 12/8/2017 | 12/22/2017
RA-PE - EE06 -04 | EE06:EnrollProvider - Service Specification | API Specification | 12/22/2017 | 1/5/2018
RA-PE - EE07 -01 | EE07:DisenrollProvider - Activity Information Flow | Process Flow (Activity) | 10/13/2017 | 10/27/2017
RA-PE - EE07 -02 | EE07:DisenrollProvider - Functional Decomposition of Performer | Process Flow (Functions) | 11/17/2017 | 12/1/2017
RA-PE - EE07 -03 | EE07:DisenrollProvider - Resource Decomposition | Object/Resource Definition | 12/15/2017 | 12/29/2017
RA-PE - EE07 -04 | EE07:DisenrollProvider - Service Specification | API Specification | 12/29/2017 | 1/12/2018
RA-PE - EE08 -01 | EE08:InquireProviderInformation - Activity Information Flow | Process Flow (Activity) | 10/20/2017 | 11/3/2017
RA-PE - EE08 -02 | EE08:InquireProviderInformation - Functional Decomposition of Performer | Process Flow (Functions) | 11/24/2017 | 12/8/2017
RA-PE - EE08 -03 | EE08:InquireProviderInformation - Resource Decomposition | Object/Resource Definition | 12/22/2017 | 1/5/2018
RA-PE - EE08 -04 | EE08:InquireProviderInformation - Service Specification | API Specification | 1/5/2018 | 1/19/2018
RA-PM- PM01 -01 | PM01:ManageProviderInformation - Activity Information Flow | Process Flow (Activity) | 12/29/2017 | 1/12/2018
RA-PM- PM01 -02 | PM01:ManageProviderInformation - Functional Decomposition of Performer | Process Flow (Functions) | 1/19/2018 | 2/2/2018
RA-PM- PM01 -03 | PM01:ManageProviderInformation - Resource Decomposition | Object/Resource Definition | 2/2/2018 | 2/16/2018
RA-PM- PM01 -04 | PM01:ManageProviderInformation - Service Specification | API Specification | 2/16/2018 | 3/2/2018

## Slide 7: Domain-specific Service Definition Schedules
CNSI (continued)
Epic # | Epic Name | Deliverable | Draft Version Release Date | Final Version Release Date
RA-PM- PM02 -01 | PM02:ManageProviderCommunication - Activity Information Flow | Process Flow (Activity) | 1/5/2018 | 1/19/2018
RA-PM- PM02 -02 | PM02:ManageProviderCommunication - Functional Decomposition of Performer | Process Flow (Functions) | 1/26/2018 | 2/9/2018
RA-PM- PM02 -03 | PM02:ManageProviderCommunication - Resource Decomposition | Object/Resource Definition | 2/9/2018 | 2/23/2018
RA-PM- PM02 -04 | PM02:ManageProviderCommunication - Service Specification | API Specification | 2/23/2018 | 3/9/2018
RA-PM- PM03 -01 | PM03:PerformProviderOutreach - Activity Information Flow | Process Flow (Activity) | 1/12/2018 | 1/26/2018
RA-PM- PM03 -02 | PM03:PerformProviderOutreach - Functional Decomposition of Performer | Process Flow (Functions) | 2/2/2018 | 2/16/2018
RA-PM- PM03 -03 | PM03:PerformProviderOutreach - Resource Decomposition | Object/Resource Definition | 2/16/2018 | 3/2/2018
RA-PM- PM03 -04 | PM03:PerformProviderOutreach - Service Specification | API Specification | 3/2/2018 | 3/16/2018
RA-PM- PM07 -01 | PM07:ManageProviderGrievanceAndAppeal - Activity Information Flow | Process Flow (Activity) | 1/19/2018 | 2/2/2018
RA-PM- PM07 -02 | PM07:ManageProviderGrievanceAndAppeal - Functional Decomposition of Performer | Process Flow (Functions) | 2/9/2018 | 2/23/2018
RA-PM- PM07 -03 | PM07:ManageProviderGrievanceAndAppeal - Resource Decomposition | Object/Resource Definition | 2/23/2018 | 3/9/2018
RA-PM- PM07 -04 | PM07:ManageProviderGrievanceAndAppeal - Service Specification | API Specification | 3/9/2018 | 3/23/2018
RA-PM- PM08 -01 | PM08:TerminateProvider - Activity Information Flow | Process Flow (Activity) | 1/26/2018 | 2/9/2018
RA-PM- PM08 -02 | PM08:TerminateProvider - Functional Decomposition of Performer | Process Flow (Functions) | 2/16/2018 | 3/2/2018
RA-PM- PM08 -03 | PM08:TerminateProvider - Resource Decomposition | Object/Resource Definition | 3/2/2018 | 3/16/2018
RA-PM- PM08 -04 | PM08:TerminateProvider - Service Specification | API Specification | 3/16/2018 | 3/30/2018