## Slide 1: Agenda
Welcome!
Status roundtable
Demo of Poplin reference implementation (messaging)
Next week

## Slide 2: Welcome!
MITA-TAC (Dave Walsh)
ONC (Arun Natarajan, Chris Muir)

## Slide 3: Status Roundtable - CNSI
Last week:
This week:
Blockers?:
Epic # | Epic Name | Deliverable | Planned Draft Version Release Date | Planned Final Version Release Date | Status | Actual Draft Version Released Date | Actual Final Version Released Date
RA-PE - EE05 -01 | EE05:DetermineProviderEligibility - Activity Information Flow | Process Flow (Activity) | 9/29/2017 | 10/13/2017 | 100% | 9/29/2017 | 
RA-PE - EE05 -02 | EE05:DetermineProviderEligibility - Functional Decomposition of Performer | Process Flow (Functions) | 11/3/2017 | 11/17/2017 | 10% |  | 
RA-PE - EE05 -03 | EE05:DetermineProviderEligibility - Resource Decomposition | Object/Resource Definition | 12/1/2017 | 12/15/2017 |  |  | 
RA-PE - EE05 -04 | EE05:DetermineProviderEligibility - Service Specification | API Specification | 12/15/2017 | 12/29/2017 |  |  | 
RA-PE - EE06 -01 | EE06:EnrollProvider - Activity Information Flow | Process Flow (Activity) | 10/6/2017 | 10/20/2017 | 75% |  | 
RA-PE - EE06 -02 | EE06:EnrollProvider - Functional Decomposition of Performer | Process Flow (Functions) | 11/10/2017 | 11/24/2017 |  |  | 
RA-PE - EE06 -03 | EE06:EnrollProvider - Resource Decomposition | Object/Resource Definition | 12/8/2017 | 12/22/2017 |  |  | 
RA-PE - EE06 -04 | EE06:EnrollProvider - Service Specification | API Specification | 12/22/2017 | 1/5/2018 |  |  | 
RA-PE - EE07 -01 | EE07:DisenrollProvider - Activity Information Flow | Process Flow (Activity) | 10/13/2017 | 10/27/2017 | 75% |  | 
RA-PE - EE07 -02 | EE07:DisenrollProvider - Functional Decomposition of Performer | Process Flow (Functions) | 11/17/2017 | 12/1/2017 |  |  | 
RA-PE - EE07 -03 | EE07:DisenrollProvider - Resource Decomposition | Object/Resource Definition | 12/15/2017 | 12/29/2017 |  |  | 
RA-PE - EE07 -04 | EE07:DisenrollProvider - Service Specification | API Specification | 12/29/2017 | 1/12/2018 |  |  | 
RA-PE - EE08 -01 | EE08:InquireProviderInformation - Activity Information Flow | Process Flow (Activity) | 10/20/2017 | 11/3/2017 | 20% |  | 
RA-PE - EE08 -02 | EE08:InquireProviderInformation - Functional Decomposition of Performer | Process Flow (Functions) | 11/24/2017 | 12/8/2017 |  |  | 
RA-PE - EE08 -03 | EE08:InquireProviderInformation - Resource Decomposition | Object/Resource Definition | 12/22/2017 | 1/5/2018 |  |  | 
RA-PE - EE08 -04 | EE08:InquireProviderInformation - Service Specification | API Specification | 1/5/2018 | 1/19/2018 |  |  | 

## Slide 4: Status Roundtable - MITRE
Last week: First draft of guidance to MITA Governance Board for MITA TA and IA based on Poplin goals, principles, practices. Debugged message testing for Poplin reference implementation and demonstration. Received intention of MITA-TAC to join Poplin WG working on UX guidelines. Continued to follow up with WEX Health on commitment to address Finance functional area.
This week: Review and release draft guidance to MITA Governance Board for MITA Technical Architecture and Information Architecture. Continue to develop Poplin reference implementation demo. Start review of pre-certification items that could be automated in a reference architecture implementation.
Blockers?: None

## Slide 5: Status Roundtable – New Mexico
Last week:
This week:
Blockers?:

## Slide 6: Status Roundtable – Vermont
Last week: Making use of messaging area
This week: Continue work on use of messaging area, 18F project status
Blockers?: None

## Slide 7: Status Roundtable – West Virginia
Last week: Focus on big procurement and how it is related to Poplin
This week: Continued on same
Blockers?: None, kick off work in November

## Slide 8: Status Roundtable – MITA-TAC
Last week: in process of outline on how TAC can participate in UX definitions
This week: continuing to work on same (mid next week)
Blockers?: none

## Slide 9: Demo of Poplin Reference Implementation (messaging)
MITRE

## Slide 10: Next week
Guidance recommendations to MITA Governance Board by 10/20/2017
Work plan from MITA-TAC on UX guidance
Continue collaboration with MTA, CDC Foundation Services team
Ongoing work
  Continual progress on functional areas
  Make sure Pivotal Tracker is updated