## Slide 1: Agenda
Roll call
Update on WEX Health
Status roundtable
Functional Area Review
Schedule review
Data Service Taxonomy vote result
Challenges for Poplin
Case Management Update – Vermont
Claims Work Breakdown – Coherence, Wily Fox, General Dynamics IT
Open Discussion

## Slide 2: Roll Call
Member | Present?
Blu Strategies Consulting | No
Coherence | No
CMS | No
General Dynamics IT | Yes
HealthTech Solutions | No
MITRE | Yes
MTA | No
Social Interest Solutions | Yes
Vermont | Yes
West Virginia | No
Wily Fox | No

## Slide 3: Update on WEX Health
Have a really big implementation going that unexpectedly needs additional resources
Can’t participate in the Poplin Working Group until mid-October
WEX Health sees the value and believes in the vision of Poplin
  Sales team and engineering team are excited about the opportunities
  Wants to increase level of support next year and add several resources
Will continue to participate in the monthly update meetings
Willing to help out in reviewing service definitions

## Slide 4: Status Roundtable - MITRE
Last week:
  Kicked off work on automated test tool, completed first sprint, burndown
  Implemented some initial proof of concept automated tests
  Started UX design on client app for interstate interoperability/eligibility use case
  Held meetings with CAQH, Change Healthcare, Softheon about joining Poplin
  Presented Poplin Working Group changes to MITA 3.0 Release 2 to CMS
This week:
  MITRE internal project all-hands Monday thru Wednesday
  Start UX design on client app
  Resume work on Pharmacy service definition
Blockers: None

## Slide 5: Status Roundtable – Vermont
Last week: Vacationing in Florida
This week: Produce final list of activities to be
presented to cover Care and Case processes to be
exposed by API’s.
Blockers: Time

## Slide 6: Status Roundtable – West Virginia
Last week:
This week:
Blockers:

## Slide 7: Status Roundtable – Blu Strategies
Last week:
This week:
Blockers:

## Slide 8: Status Roundtable – HealthTech Solutions
Last week: No status
This week: Determine functional area breakdown and assignments
Blockers: None

## Slide 9: Status Roundtable – Social Interest Solutions
Last week: We are working on our approach for alternate work breakdown for DW/BI work.
This week: Work with partners on work breakdown.
Blockers: None

## Slide 10: Status Roundtable – General Dynamics IT
Last week: Slowed by key resources out due to illness, vacation, other work.
This week:
  delay on delivery of claim break down - target date of feedback 5/1
  delay on delivery of Data Services Taxonomy - target date of feedback 5/3
Blockers: Key resources engaged in other work or out of office

## Slide 11: Status Roundtable – Wily Fox
Last week: Reviewed and commented on the initial Claims Area decomposition matrix.
This week: Meet with Coherence to come up with a claims processing decomposition list so that we can move forward with assignment.
Blockers: None

## Slide 12: Status Roundtable - Coherence
Last week: Collected feedback on Claims Area decomposition matrix.
This week: Meet with Wily Fox to come up with a claims processing decomposition list so that we can move forward with assignment.
Blockers: None

## Slide 13: Functional Areas Divide and Conquer Approach
Functional Area | Covered | Member
Case Management |  | Vermont
Claims |  | Wily Fox, Coherence, General Dynamics IT
Data Warehouse / Business Intelligence / Analytics |  | Blu Strategies, Social Interest Solutions, HealthTech Solutions
Electronic Visit Verification (EVV) |  | MITRE
Financial Management | HOLD | WEX Health
Member Eligibility |  | West Virginia
Pharmacy |  | MITRE
Provider Screening |  | General Dynamics IT
Shared Services: Messaging, Registration/Discovery, Security |  | MITRE
Identity Management | OPEN | 
Managed Care Enrollment Broker | OPEN | 
Member Enrollment | OPEN | 
Provider Enrollment | OPEN | 
Third Party Liability | OPEN | 
13

## Slide 14: Poplin Working Group Schedule
Poplin Member | Deliverable | Due Date
Blu Strategies, Social Interest, HealthTech | Data Service Taxonomy – Final Candidate | DONE!
General Dynamics IT | Draft Identity Management White Paper | May 8, 2018
Vermont | Case Management: Client/Member Management Service Definition Draft | May 11, 2018
Vermont | Case Management: Service Management Service Definition Draft | May 11, 2018
Vermont | Case Management: Eligibility and Enrollment Service Definition Draft | May 11, 2018
Blu Strategies, Social Interest, HealthTech | Data Warehouse / Business Intelligence / Analytics Service Definitions | May 11, 2018
Wily Fox, Coherence | Claims Service Definitions - Draft | May 11, 2018
General Dynamics IT | Provider Screening Service Definitions - Draft | TBD
West Virginia | Member Eligibility Service Definitions - Draft | TBD

## Slide 15: Vote – Data Service Taxonomy Document Approved!
Member | Vote
Blu Strategies Consulting | Yes
Coherence | Yes
CMS | -
General Dynamics IT | Abstain
HealthTech Solutions | Yes
MITRE | Yes
Social Interest Solutions | Yes
Vermont | Yes
West Virginia | -
Wily Fox | Yes

## Slide 16: Challenges for Poplin
Resources and time within the Poplin members with competing priorities (3x)
How are states going to adopt the service definitions
  Challenges around adoption given states are at different states in modularity path
  How do we get traction?
Which modules to implement?
How do legacy systems apply the new APIs?
CMS funding for updating MES systems to support APIs
Modularity map, breaking down each functional area, to know
  What APIs we have left to cover
  When are we done?
Determining gold sources of data?
Managing baselines, extensions, and profiles going forward
Terminology and naming conventions
Building and reaching consensus
Keeping meta-model up to date
  Process for keeping service definitions current and updated

## Slide 17: Case Management Update
Vermont

## Slide 18: Claims Work Breakdown
Coherence, Wily Fox, General Dynamics IT

## Slide 19: Open Discussion