## Slide 1: Agenda
Administravia
  Roll call
  Status roundtable
  Functional area review
  Schedule review
Challenges for Poplin
  Terminology and naming conventions
Demo
  Eligibility use case UX design
Open discussion

## Slide 2: Roll Call
Member | Present?
Blu Strategies Consulting | 
CAQH | 
Coherence | 
CMS | 
General Dynamics IT | 
HealthTech Solutions | 
HMS | 
Magellan | 
MITA-TAC | 
MITRE | 
MTA | 
Social Interest Solutions | 
Vermont | 
West Virginia | 
Wily Fox | 

## Slide 3: Status Roundtable – General Project MITRE
Last week:
  EHR-LLC has joined Poplin to help with ThreadBear!
  Conducted meetings with provider screening group, data services group
This week:
  Meeting to discuss object repository for Poplin project
    Web site, hosting, etc.
Blockers:
  None

## Slide 4: Status Roundtable – Member Eligibility / Demo West Virginia, MITRE
Last week:
  Reviewed rough draft of fraud detection APIs
  Completed UX workflow diagrams for client application
  Created React/Redux framework for client application
  Created API framework for mock eligibility service to interact with WV system
This week:
  Sprint burn-down
  Complete hi-fidelity wireframes for client application
  Complete UX information architecture for client application
  Continue refining resources and fields for fraud detection API
  Implement data models in mock eligibility service
Blockers:
  None

## Slide 5: Status Roundtable – ThreadBear Test Tool / Demo MITRE
Last week:
  Worked on object modeling
  Further work on UI
  Debugged Docker scripts for Provider Screening Module
  Instantiated local instance of Provider Screening Module in Docker
This week:
  Implement top-down validations to better work with UI
  Become more familiar with Provider Screening Module code
  Start expanding the API framework for Provider Screening Module
  Document Docker setup
Blockers:
  None

## Slide 6: Status Roundtable – Case Management Vermont
Last week:
  Unable to make progress this week
This week:
  Continue reviewing case type specific activities and defining resources to cover the standard activity specific information needs
Blockers:
  Resource constraints

## Slide 7: Status Roundtable – Data Services Blu Strategies, Social Interest Solutions, HealthTech Solutions
Last week:
  Not able to make progress
This week:
  Task lists for data warehouse, data collection, data distribution architecture for Pivotal Tracker
Blockers:
  Resource constraints

## Slide 8: Status Roundtable – Claims Coherence, Wily Fox, General Dynamics IT
Last week:
  Began work on Basic Validation Service (concept).
  Worked on Provider Validation Service task list for Pivotal Tracker
This week:
  Continue work on Basic Validation Service
  Task lists for Pivotal Tracker
Blockers:
  None

## Slide 9: Status Roundtable – Pharmacy Magellan, MITRE
Last week:
  Magellan met with MITRE, Jeff Cook 5/25 to review the current draft of our service definition document and diagram.
This week:
  We will make sure we’re all in agreement as to the direction, and get more specific about the scope of the 6/30 deliverable.
Blockers:
  None

## Slide 10: Status Roundtable – Provider Screening General Dynamics IT, CAQH, MITRE
Last week:
  Held meeting to discussion service breakdown
This week:
  Review critical points of service breakdown
  Determine service breakdown and initial assignments of members
Blockers:
  None

## Slide 11: Status Roundtable – Third Party Liability HMS
Last week:
This week:
Blockers:

## Slide 12: Functional Areas Divide and Conquer Approach
Functional Area | Covered | Member
Case Management |  | Vermont
Claims (21 total services identified) |  | 
Basic Validation Service |  | Wily Fox
CCI Validator Service |  | Wily Fox
Claims Financial Services Service |  | Coherence
DRG Grouper Service |  | Coherence
Duplicate Check Service |  | Wily Fox
Provider Validation Service |  | General Dynamics IT
Service Frequency Limitation Check Service |  | Wily Fox
Data Services (8 total subareas identified) |  | 
Data Warehouse |  | Social Interest Solutions
Data Collection |  | HealthTech Solutions
Data Distribution |  | HealthTech Solutions
Electronic Visit Verification (EVV) |  | MITRE
Financial Management | HOLD | WEX Health
Member Eligibility |  | West Virginia, MITRE
12

## Slide 13: Functional Areas Divide and Conquer Approach
Functional Area | Covered | Member
Pharmacy |  | Magellan, MITRE
Provider Screening |  | General Dynamics IT, CAQH, MITRE
Shared Services: Messaging, Registration/Discovery, Security |  | MITRE
Third Party Liability |  | HMS
Identity Management | OPEN | General Dynamics IT (white paper)
Managed Care Enrollment Broker | OPEN | MTA members have expressed interest
Member Enrollment | OPEN | Social Interest has expressed interest
Provider Enrollment | OPEN | 
13

## Slide 14: Poplin Working Group Schedule
Poplin Member | Deliverable | Due Date
MITRE | ThreadBear Automated Test Tool Initial Demo | DONE
Wily Fox | Task list and durations for basic claim validation service definition | May 25, 2018
Wily Fox | Task list and durations for duplicate check service definition | May 25, 2018
Wily Fox | Task list and durations for service frequency limitation check service def. | May 25, 2018
GDIT | Task list and durations for provider validation service definition | May 25, 2018
Coherence | Task list and durations for DRG group service definition | May 25, 2018
Coherence | Task list and durations for claims financial services service definition | May 25, 2018
Vermont | Case Management: Client/Member Management Service Definition Draft | June 29, 2018
Vermont | Case Management: Service Management Service Definition Draft | June 29, 2018
Vermont | Case Management: Eligibility and Enrollment Service Definition Draft | June 29, 2018
Social Interest Solutions | Task list and durations for data warehouse service definition | TBD
HealthTech Solutions | Task list and durations for data collection service definition | TBD
HealthTech Solutions | Task list and durations for data distribution service definition | TBD
Notes: Arvinder has aggregated all of the tasks and durations – push to next Friday

## Slide 15: Poplin Working Group Schedule (continued)
Poplin Member | Deliverable | Due Date
GDIT, MITRE | Provider Screening Service Definitions - Draft | June 15, 2018
West Virginia, MITRE | Member Eligibility Service Definitions - Draft | June 15, 2018
Magellan, MITRE | Pharmacy Service Definitions - Draft | June 29, 2018
MITRE | Interstate Eligibility Use Case Initial Demo | July 21, 2018
MITRE | ThreadBear Automated Test Tool MESC Demo | August 10, 2018
MITRE | Interstate Eligibility Use Case MESC Demo | August 10, 2018

## Slide 16: Challenges for Poplin
Terminology and naming conventions

## Slide 17: Eligibility Use Case UX Design
MITRE

## Slide 18: Open Discussion