## Slide 1: Agenda
Status roundtable
Pivotal Tracker walk through
Functional areas
MESC update
Project name
Next week

## Slide 2: Status Roundtable - CNSI
Last week:
This week: Putting together service and object definitions for the Provider Management module
Blockers? None
Iteration | Story No. | Story Title | Story | Estimate | % Completion
7/17/2017 |  |  |  |  | 
IT01 | RA-IT01-001 | Develop business process for Provide Module | Create the business process diagram for the Provider Module | 2 | 50%
IT01 | RA-IT01-002 | Identify list of service/API for Provider Module | Identify the list of services required for the Provider module | 2 | 90%
IT01 | RA-IT01-003 | Identify list of objects for Provider Module | Identify the list of objects required for the Provider Module | 2 | 90%
IT01 | RA-IT01-004 | Document Provider Module - Business Process | Document the business process developed and get it ready for presentation | 0.5 | 25%
IT01 | RA-IT01-005 | Document Provider Module - Objects | Document the objects identified and get it ready for presentation | 0.5 | 90%
IT01 | RA-IT01-006 | Document Provider Module - Services/APIs | Document the Services/APIs identified and get it ready for presentation | 1 | 90%

## Slide 3: Status Roundtable - MITRE
Last week: Investigated open source communication / messaging solutions (Apache Kafka, RabbitMQ), consolidating VT and MITRE template documents, setup Pivotal Tracker instance for RA and captured schedules, incorporated service definition templates into MESC presentation.
  Platform as a Service
    Red Hat OpenShift (Docker, Kubernetes)
  Communication / Messaging
    Apache Kafka, RabbitMQ
  Registration / Discovery
    Kubernetes, Consul, Hyperbahn, ZooKeeper
  Security – longer term…
    Heart Working Group, Argonauts, OAuth2, OpenID Connect, User Managed Access (UMA, Kantara), SAML
This week: Investigate open source service registration and discovery solutions
Blockers?: None

## Slide 4: Status Roundtable - Vermont
Last week: Delivered schedule
This week: Starting service management process definition sprint, using Pivotal Tracker
Blockers?: How should Vermont best participate
Task | Status | Assigned To | LOE SWAG (S/M/L/XL) | Due Date | Comments/Notes | Sprint count
Case Management Service Definition |  |  |  |  |  | 
Client/Member Management |  |  |  | 12/1/17 |  | 
Process definitions - Process flow diagrams, Process descriptions (UML) | Not Started | CJ, Tim, Andrew | L | 10/20/17 | 7 high-level processes in MM | 2
Object definitions - Context, class, interaction, ER diagrams (UML / SysML) | Not Started | CJ, Tim, Andrew | L | 11/3/17 |  | 3
Resource definitions - Sample resource template with required fields | Not Started | CJ, Tim, Andrew | M | 11/27/17 |  | 1
API Specification - Sample API spec with required fields | Not Started | CJ, Tim, Andrew | M | 11/27/17 |  | 1
Service Management | In Progress |  |  | 10/1/17 |  | 
Process definitions - Process flow diagrams, Process descriptions (UML) | Not Started | CJ, Tim, Andrew | XL | 8/25/17 | 19 high-level processes in Care Management. 1 high-level process in Operations Management. Several interactions with other areas. | 2
Object definitions - Context, class, interaction, ER diagrams (UML / SysML) | Not Started | CJ, Tim, Andrew | XL | 9/8/17 |  | 2
Resource definitions - Sample resource template with required fields | Not Started | CJ, Tim, Andrew | L | 9/15/17 |  | 3
API Specification - Sample API spec with required fields | Not Started | CJ, Tim, Andrew | L | 9/22/17 |  | 1
Eligibility & Enrollment |  |  |  | 12/1/17 | 5 high-level processes | 
Process definitions - Process flow diagrams, Process descriptions (UML) | Not Started | CJ, Tim, Andrew | XL | 10/20/17 |  | 2
Object definitions - Context, class, interaction, ER diagrams (UML / SysML) | Not Started | CJ, Tim, Andrew | XL | 11/3/17 |  | 3
Resource definitions - Sample resource template with required fields | Not Started | CJ, Tim, Andrew | L | 11/27/17 |  | 1
API Specification - Sample API spec with required fields | Not Started | CJ, Tim, Andrew | L | 11/27/17 |  | 1

## Slide 5: Status Roundtable - Molina
Last week: Put together question list and determine next steps
This week:
Blockers?: None for now

## Slide 6: Pivotal Tracker Walk Through
Pace Ricciardelli
The MITRE Corporation

## Slide 7: MESC Update
Medicaid Reference Architecture Preconference Session
  August 14, 2017
  Incorporated service definition template work into presentation
  Will continue to integrate latest status until presentation time
  Encourage Working Group members to attend!

## Slide 8: Project Name
Poplin (#POPLIN)
  pop·lin
    noun: a plain-woven fabric, typically a lightweight cotton, with a corded surface
    Durable poplin fabric is often used to create scrubs for clinical staff. The POPLIN project seeks to develop a cohesive, free, open-source reference architecture for states to use in developing a modern, modular Medicaid system. It is our hope that the POPLIN project serves as the underlying connective fabric for future Medicaid systems.
Corduroy
MESRA – Medicaid Enterprise System Reference Architecture
AMIE - Advanced Medicaid Integration Environment

## Slide 9: Next week
Start of next sprint
  Sprint plans
  Continual progress on functional areas
  Capture sprints for service definition work into project tracking tool
Project name
  Project logo
  MESC conference
  Project web site design