## Slide 1: Agenda
Status roundtable
Demo of Inquire Provider Information Business Flow (CNSI)
Next week

## Slide 2: Status Roundtable - CNSI
Last week:
This week:
Blockers?:
Epic # | Epic Name | Deliverable | Draft Version - Planned Release Date | Final Version - Planned Release Date | Status | Draft Version - Actual Released Date | Final Version - Actual Released Date
RA-PE - EE05 -01 | EE05:DetermineProviderEligibility - Activity Information Flow | Process Flow (Activity) | 9/29/2017 | 10/13/2017 | 100% | 9/29/2017 | 10/13/2017
RA-PE - EE05 -02 | EE05:DetermineProviderEligibility - Functional Decomposition of Performer | Process Flow (Functions) | 11/3/2017 | 11/17/2017 | 20% |  | 
RA-PE - EE05 -03 | EE05:DetermineProviderEligibility - Resource Decomposition | Object/Resource Definition | 12/1/2017 | 12/15/2017 | 10% |  | 
RA-PE - EE05 -04 | EE05:DetermineProviderEligibility - Service Specification | API Specification | 12/15/2017 | 12/29/2017 |  |  | 
RA-PE - EE06 -01 | EE06:EnrollProvider - Activity Information Flow | Process Flow (Activity) | 10/6/2017 | 10/20/2017 | 100% | 10/6/2017 | 10/20/2017
RA-PE - EE06 -02 | EE06:EnrollProvider - Functional Decomposition of Performer | Process Flow (Functions) | 11/10/2017 | 11/24/2017 |  |  | 
RA-PE - EE06 -03 | EE06:EnrollProvider - Resource Decomposition | Object/Resource Definition | 12/8/2017 | 12/22/2017 |  |  | 
RA-PE - EE06 -04 | EE06:EnrollProvider - Service Specification | API Specification | 12/22/2017 | 1/5/2018 |  |  | 
RA-PE - EE07 -01 | EE07:DisenrollProvider - Activity Information Flow | Process Flow (Activity) | 10/13/2017 | 10/27/2017 | 75% | 10/13/2017 | 
RA-PE - EE07 -02 | EE07:DisenrollProvider - Functional Decomposition of Performer | Process Flow (Functions) | 11/17/2017 | 12/1/2017 |  |  | 
RA-PE - EE07 -03 | EE07:DisenrollProvider - Resource Decomposition | Object/Resource Definition | 12/15/2017 | 12/29/2017 |  |  | 
RA-PE - EE07 -04 | EE07:DisenrollProvider - Service Specification | API Specification | 12/29/2017 | 1/12/2018 |  |  | 
RA-PE - EE08 -01 | EE08:InquireProviderInformation - Activity Information Flow | Process Flow (Activity) | 10/20/2017 | 11/3/2017 | 75% | 10/20/2017 | 
RA-PE - EE08 -02 | EE08:InquireProviderInformation - Functional Decomposition of Performer | Process Flow (Functions) | 11/24/2017 | 12/8/2017 |  |  | 
RA-PE - EE08 -03 | EE08:InquireProviderInformation - Resource Decomposition | Object/Resource Definition | 12/22/2017 | 1/5/2018 |  |  | 
RA-PE - EE08 -04 | EE08:InquireProviderInformation - Service Specification | API Specification | 1/5/2018 | 1/19/2018 |  |  | 
Notes: Last week: Inquire business flow
Next week: detrmeinr provider eligibility object and resource, document in two weeks
Blockers:

## Slide 3: Status Roundtable - MITRE
Last week: Reviewed and released draft guidance to MITA Governance Board for MITA Technical Architecture and Information Architecture. Continue to develop Poplin reference implementation demo, particularly messaging across clusters. Start review of pre-certification items that could be automated in a reference architecture implementation. Received work plan from MITA-TAC and returned comments. Received commitment from WEX Health to work on Financial Management functional area. Social Interest Solutions, Blu Strategies Consulting, and HMS Healthcare has expressed interest in joining the group.
This week: Obtain commitments, functional area selections, and schedules from Social Interest Solutions, Blu Strategies, and HMS; develop plan for follow-on reference implementation work; start work on security shared service.
Blockers?: None

## Slide 4: Status Roundtable - ONC
Last week:
This week:
Blockers?:
Notes: Al Taylor will be representing ONC and working to advance the standards
Embed Al in ongoing efforts
No blockers

## Slide 5: Status Roundtable – Vermont
Last week:
This week:
Blockers?:
Notes: Last week: On track for early December , Andrew’s role has changed, bringing Poplin to Digital Serivces
This week: meeting between Poplln and VT Digital Services (engagement with 18F)
No blockers

## Slide 6: Status Roundtable – West Virginia
Last week:
This week:
Blockers?:
Notes: Last week: Large procurement that fits in strategic vision that fits in with Poplin project with member module
This week: Anticipate a reward any moment on procurement, getting the work underway and have project schedule for providing service definitions. Working on identifying a problem that we can solve with Poplin (Opioid-related?).
Blockers: None

## Slide 7: EE08: Inquire Provider Information Business Flow
CNSI

## Slide 8: Next week
Guidance recommendations to MITA Governance Board by 10/20/2017
Revised work plan from MITA-TAC on UX guidance
Recruit new members
Continue collaboration with MTA, CDC Foundation Services team
Ongoing work
  Continual progress on functional areas
  Make sure Pivotal Tracker is updated