## Slide 1: Agenda
Status roundtable
Functional area update
Next week

## Slide 2: Status Roundtable - CNSI
Last week:
This week:
Blockers?:
Epic # | Epic Name | Deliverable | Draft Version - Planned Release Date | Final Version - Planned Release Date | Status | Draft Version - Actual Released Date | Final Version - Actual Released Date
RA-PE - EE05 -01 | EE05:DetermineProviderEligibility - Activity Information Flow | Process Flow (Activity) | 9/29/2017 | 10/13/2017 | 100% | 9/29/2017 | No Change from the Draft Version
RA-PE - EE05 -02 | EE05:DetermineProviderEligibility - Functional Decomposition of Performer | Process Flow (Functions) | 11/3/2017 | 11/17/2017 | 60% |  | 
RA-PE - EE05 -03 | EE05:DetermineProviderEligibility - Resource Decomposition | Object/Resource Definition | 12/1/2017 | 12/15/2017 | 20% |  | 
RA-PE - EE05 -04 | EE05:DetermineProviderEligibility - Service Specification | API Specification | 12/15/2017 | 12/29/2017 |  |  | 
RA-PE - EE06 -01 | EE06:EnrollProvider - Activity Information Flow | Process Flow (Activity) | 10/6/2017 | 10/20/2017 | 100% | 10/6/2017 | No Change from the Draft Version
RA-PE - EE06 -02 | EE06:EnrollProvider - Functional Decomposition of Performer | Process Flow (Functions) | 11/10/2017 | 11/24/2017 |  |  | 
RA-PE - EE06 -03 | EE06:EnrollProvider - Resource Decomposition | Object/Resource Definition | 12/8/2017 | 12/22/2017 |  |  | 
RA-PE - EE06 -04 | EE06:EnrollProvider - Service Specification | API Specification | 12/22/2017 | 1/5/2018 |  |  | 
RA-PE - EE07 -01 | EE07:DisenrollProvider - Activity Information Flow | Process Flow (Activity) | 10/13/2017 | 10/27/2017 | 100% | 10/13/2017 | No Change from the Draft Version
RA-PE - EE07 -02 | EE07:DisenrollProvider - Functional Decomposition of Performer | Process Flow (Functions) | 11/17/2017 | 12/1/2017 |  |  | 
RA-PE - EE07 -03 | EE07:DisenrollProvider - Resource Decomposition | Object/Resource Definition | 12/15/2017 | 12/29/2017 |  |  | 
RA-PE - EE07 -04 | EE07:DisenrollProvider - Service Specification | API Specification | 12/29/2017 | 1/12/2018 |  |  | 
RA-PE - EE08 -01 | EE08:InquireProviderInformation - Activity Information Flow | Process Flow (Activity) | 10/20/2017 | 11/3/2017 | 75% | 10/20/2017 | 
RA-PE - EE08 -02 | EE08:InquireProviderInformation - Functional Decomposition of Performer | Process Flow (Functions) | 11/24/2017 | 12/8/2017 |  |  | 
RA-PE - EE08 -03 | EE08:InquireProviderInformation - Resource Decomposition | Object/Resource Definition | 12/22/2017 | 1/5/2018 |  |  | 
RA-PE - EE08 -04 | EE08:InquireProviderInformation - Service Specification | API Specification | 1/5/2018 | 1/19/2018 |  |  | 
Notes: Last week: Cointinuing identifying fucntions for provider eligibility – good progress. List of functions next week
Next week: List of functions
Blockers: None

## Slide 3: Status Roundtable - MITRE
Last week: Feedback positive from MITA Governance Board submission. Continued to debug Poplin messaging across clusters. Continued review of pre-certification items that could be automated in a reference architecture implementation. Started work on security shared service(s) and next steps for reference implementation. High level flow identified and created for Pharmacy functional area, working on micro services/ sub processes needed to accomplish the overall processes, using Ohio’s new pharmacy documentation as the basis. Worked with MITA-TAC on scoping UX plan. Met with CDC Foundation Services to learn specifics on 12 shared services they are developing and overall architecture. Social Interest Solutions is working on what level of commitment they can provide (Enrollment, Identity Management), Blu Strategies Consulting (Analytics, Business Intelligence). HMS Healthcare will be added to monthly update meetings. CA Technologies has expressed interest in Poplin.
This week: Start full MITA Governance Board review of draft Poplin guidance. Obtain commitments, definitive functional area selections, and schedules from Social Interest Solutions, Blu Strategies; follow up with CA Technologies and interest; develop schedule for follow-on reference implementation work; develop schedule for security shared service(s).
Blockers?: None

## Slide 4: Status Roundtable - ONC
Last week:
This week:
Blockers?:
Notes: Last week: Introduced Al Taylor to the group, he will become the point person, began reviewing guidance document
Next week: review document
Blockers: none

## Slide 5: Status Roundtable – Vermont
Last week:
This week:
Blockers?:
Notes: Last week: Continuing to identify services that Case management depends on (80 services+)
This week: Continuing to identify services that Case management depends on
Blockers: None

## Slide 6: Status Roundtable – West Virginia
Last week:
This week:
Blockers?:
Notes: Last week: Large procurement that fits in strategic vision that fits in with Poplin project with member module
This week: Anticipate a reward any moment on procurement, getting the work underway and have project schedule for providing service definitions. Working on identifying a problem that we can solve with Poplin (Opioid-related?).
Blockers: None

## Slide 7: Status Roundtable – WEX Health
Last week:
This week:
Blockers?:

## Slide 8: Functional Area Update
Provider Management (CNSI)
  Screening
  Enrollment
Claims
Pharmacy (MITRE)
Financial Management (WEX Health)
Member Management
  Eligibility (West Virginia)
  Enrollment (Social Interest Solutions?)
Third Party Liability
Case Management (Vermont)
  Interaction with Eligibility & Enrollment
Data Warehouse / Business Intelligence / Analytics (Blu Strategies Consulting?)
Managed Care Enrollment Broker
Identity Management (Social Interest Solutions?)
Shared Services (MITRE)
  Service registration, service discovery, messaging, security

## Slide 9: Next week
Full review starts on guidance by MITA Governance Board
Continue to refine UX guidance plan from MITA-TAC
Recruit and follow-up with new members
Developing leveraging strategy with CDC Foundation Services team
Ongoing work
  Continual progress on functional areas
  Make sure Pivotal Tracker is updated