## Slide 1: Agenda
Status roundtable
Functional area update
EE05:DetermineProviderEligibility – Object/Resource Model Diagram (CNSI)
Automating Pre-certification Testing (MITRE)
Next week

## Slide 2: Status Roundtable - CNSI
Last week:
This week:
Blockers?:
Epic # | Epic Name | Deliverable | Draft Version - Planned Release Date | Final Version - Planned Release Date | Status | Draft Version - Actual Released Date | Final Version - Actual Released Date
RA-PE - EE05 -01 | EE05:DetermineProviderEligibility - Activity Information Flow | Process Flow (Activity) | 9/29/2017 | 10/13/2017 | 100% | 9/29/2017 | No Change from the Draft Version
RA-PE - EE05 -02 | EE05:DetermineProviderEligibility - Functional Decomposition of Performer | Process Flow (Functions) | 11/3/2017 | 11/17/2017 | 75% | 11/3/2017 | 
RA-PE - EE05 -03 | EE05:DetermineProviderEligibility - Resource Decomposition | Object/Resource Definition | 12/1/2017 | 12/15/2017 | 30% |  | 
RA-PE - EE05 -04 | EE05:DetermineProviderEligibility - Service Specification | API Specification | 12/15/2017 | 12/29/2017 |  |  | 
RA-PE - EE06 -01 | EE06:EnrollProvider - Activity Information Flow | Process Flow (Activity) | 10/6/2017 | 10/20/2017 | 100% | 10/6/2017 | No Change from the Draft Version
RA-PE - EE06 -02 | EE06:EnrollProvider - Functional Decomposition of Performer | Process Flow (Functions) | 11/10/2017 | 11/24/2017 | 10% |  | 
RA-PE - EE06 -03 | EE06:EnrollProvider - Resource Decomposition | Object/Resource Definition | 12/8/2017 | 12/22/2017 |  |  | 
RA-PE - EE06 -04 | EE06:EnrollProvider - Service Specification | API Specification | 12/22/2017 | 1/5/2018 |  |  | 
RA-PE - EE07 -01 | EE07:DisenrollProvider - Activity Information Flow | Process Flow (Activity) | 10/13/2017 | 10/27/2017 | 100% | 10/13/2017 | No Change from the Draft Version
RA-PE - EE07 -02 | EE07:DisenrollProvider - Functional Decomposition of Performer | Process Flow (Functions) | 11/17/2017 | 12/1/2017 |  |  | 
RA-PE - EE07 -03 | EE07:DisenrollProvider - Resource Decomposition | Object/Resource Definition | 12/15/2017 | 12/29/2017 |  |  | 
RA-PE - EE07 -04 | EE07:DisenrollProvider - Service Specification | API Specification | 12/29/2017 | 1/12/2018 |  |  | 
RA-PE - EE08 -01 | EE08:InquireProviderInformation - Activity Information Flow | Process Flow (Activity) | 10/20/2017 | 11/3/2017 | 100% | 10/20/2017 | No Change from the Draft Version
RA-PE - EE08 -02 | EE08:InquireProviderInformation - Functional Decomposition of Performer | Process Flow (Functions) | 11/24/2017 | 12/8/2017 |  |  | 
RA-PE - EE08 -03 | EE08:InquireProviderInformation - Resource Decomposition | Object/Resource Definition | 12/22/2017 | 1/5/2018 |  |  | 
RA-PE - EE08 -04 | EE08:InquireProviderInformation - Service Specification | API Specification | 1/5/2018 | 1/19/2018 |  |  | 
Notes: Last week: Worked on data object for EE05
Next week: Continuing on object and model for EE06, EE07
Blockers: None

## Slide 3: Status Roundtable - MITRE
Last week: Received specific feedback from MITA Governance Board and ONC on guidance submission. Continued to debug Poplin messaging across clusters. Completed preliminary review of pre-certification items that could be automated in a reference architecture implementation. Worked on developing schedule for security shared service(s). Drafted business process diagrams for pharmacy. Worked with MITA-TAC on scoping UX plan. Blu Strategies Consulting can provide 1 FTE through end of January (Analytics, Business Intelligence). Meeting scheduled with Social Interest Solutions to discuss deliverable requirements (Enrollment, Identity Management). Meeting scheduled to discuss Poplin with CA Technologies.
This week: Address Jeff Strand’s and ONC’s comments on MGB submission. Review draft of pharmacy business process diagrams. Develop schedule for follow-on reference implementation work. Obtain commitments, definitive functional area selections, and schedules from Social Interest Solutions. Obtain schedule from Blu Strategies Consulting. Meet with CA Technologies.
Blockers?: None

## Slide 4: Status Roundtable – Vermont
Last week:
This week:
Blockers?:
Notes: Last week: Continuing to identify services that Case management depends on (80 services+).
This week: Continuing to identify services that Case management depends on
Blockers: Managing conflicting priorities

## Slide 5: Status Roundtable – West Virginia
Last week:
This week:
Blockers?:
Notes: Last week: Anticipate reward in next two weeks
This week: Anticipate a reward any moment on procurement, getting the work underway and have project schedule for providing service definitions. Working on identifying a problem that we can solve with Poplin (Opioid-related?).
Blockers: None

## Slide 6: Status Roundtable – WEX Health
Last week:
This week:
Blockers?:
Notes: Last week:
This week: Learning, developing a schedule.
Blockers?:

## Slide 7: Status Roundtable – Blu Strategies Consulting
Last week:
This week:
Blockers?:
Notes: Last week:
This week: Develop schedule (Analytics, BI)
Blockers?: None

## Slide 8: Status Roundtable - ONC
Last week:
This week:
Blockers?:
Notes: Last week: Introduced Al Taylor to the group, he will become the point person, began reviewing guidance document
Next week: review document
Blockers: none

## Slide 9: EE05:DetermineProviderEligibility – Object/Resource Model Diagram
CNSI

## Slide 10: Automating Pre-certification Testing
MITRE

## Slide 11: Functional Area Update
Provider Management (CNSI)
  Screening
  Enrollment
Claims
Pharmacy (MITRE)
Financial Management (WEX Health)
Member Management
  Eligibility (West Virginia)
  Enrollment (Social Interest Solutions?)
Third Party Liability
Case Management (Vermont)
  Interaction with Eligibility & Enrollment
Data Warehouse / Business Intelligence / Analytics (Blu Strategies Consulting)
Managed Care Enrollment Broker
Identity Management (Social Interest Solutions?)
Shared Services (MITRE)
  Service registration, service discovery, messaging, security

## Slide 12: Next week
Address comments from ONC and MITA Governance Board on guidance submission
Continue to refine UX guidance plan from MITA-TAC
Meet with Social Interest Solutions, CA Technologies about Poplin involvement
Reference implementation schedule for next steps
Ongoing work
  Continual progress on functional areas
  Make sure Pivotal Tracker is updated