## Slide 1: Agenda
Status roundtable
Functional area update
CNSI Demo: EE06: Enroll Provider – Object/Resource Model Diagram
Next week

## Slide 2: Status Roundtable - CNSI
Last week:
This week:
Blockers?:
Epic # | Epic Name | Deliverable | Draft Version - Planned Release Date | Final Version - Planned Release Date | Status | Draft Version - Actual Released Date | Final Version - Actual Released Date
RA-PE - EE05 -01 | EE05:DetermineProviderEligibility - Activity Information Flow | Process Flow (Activity) | 9/29/2017 | 10/13/2017 | 100% | 9/29/2017 | No Change from the Draft Version
RA-PE - EE05 -02 | EE05:DetermineProviderEligibility - Functional Decomposition of Performer | Process Flow (Functions) | 11/3/2017 | 11/17/2017 | 75% | 11/3/2017 | 
RA-PE - EE05 -03 | EE05:DetermineProviderEligibility - Resource Decomposition | Object/Resource Definition | 12/1/2017 | 12/15/2017 | 30% |  | 
RA-PE - EE05 -04 | EE05:DetermineProviderEligibility - Service Specification | API Specification | 12/15/2017 | 12/29/2017 |  |  | 
RA-PE - EE06 -01 | EE06:EnrollProvider - Activity Information Flow | Process Flow (Activity) | 10/6/2017 | 10/20/2017 | 100% | 10/6/2017 | No Change from the Draft Version
RA-PE - EE06 -02 | EE06:EnrollProvider - Functional Decomposition of Performer | Process Flow (Functions) | 11/10/2017 | 11/24/2017 | 10% |  | 
RA-PE - EE06 -03 | EE06:EnrollProvider - Resource Decomposition | Object/Resource Definition | 12/8/2017 | 12/22/2017 |  |  | 
RA-PE - EE06 -04 | EE06:EnrollProvider - Service Specification | API Specification | 12/22/2017 | 1/5/2018 |  |  | 
RA-PE - EE07 -01 | EE07:DisenrollProvider - Activity Information Flow | Process Flow (Activity) | 10/13/2017 | 10/27/2017 | 100% | 10/13/2017 | No Change from the Draft Version
RA-PE - EE07 -02 | EE07:DisenrollProvider - Functional Decomposition of Performer | Process Flow (Functions) | 11/17/2017 | 12/1/2017 |  |  | 
RA-PE - EE07 -03 | EE07:DisenrollProvider - Resource Decomposition | Object/Resource Definition | 12/15/2017 | 12/29/2017 |  |  | 
RA-PE - EE07 -04 | EE07:DisenrollProvider - Service Specification | API Specification | 12/29/2017 | 1/12/2018 |  |  | 
RA-PE - EE08 -01 | EE08:InquireProviderInformation - Activity Information Flow | Process Flow (Activity) | 10/20/2017 | 11/3/2017 | 100% | 10/20/2017 | No Change from the Draft Version
RA-PE - EE08 -02 | EE08:InquireProviderInformation - Functional Decomposition of Performer | Process Flow (Functions) | 11/24/2017 | 12/8/2017 |  |  | 
RA-PE - EE08 -03 | EE08:InquireProviderInformation - Resource Decomposition | Object/Resource Definition | 12/22/2017 | 1/5/2018 |  |  | 
RA-PE - EE08 -04 | EE08:InquireProviderInformation - Service Specification | API Specification | 1/5/2018 | 1/19/2018 |  |  | 
Notes: Last week: Enroll provider object diagrams
Next week: Disenroll provider diagrams, resource decompositions for provider enrollment
Blockers: None

## Slide 3: Status Roundtable - MITRE
Last week: Addressed comments on MGB submission. Reviewing draft of pharmacy business process diagrams. Met with Blu Strategies and NM to discuss analytics/BI approach. Met with CA Technologies (security) and sent template and example service definitions. Met with Henry Chao, who is interested in eligibility and third-party liability. Worked on developing schedule for security shared service(s). Worked with MITA-TAC on scoping UX plan. Meeting rescheduled with Social Interest Solutions to discuss deliverable requirements (Enrollment, Identity Management).
This week: Obtain commitments, definitive functional area selections, and schedules from Social Interest Solutions, CA Technologies, Henry Chao. Release updates to MGB. Develop schedule for follow-on reference implementation work.
Blockers?: None

## Slide 4: Status Roundtable – Vermont
Last week:
This week:
Blockers?:
Notes: Last week: Continuing to identify services that Case management depends on (80 services+).
This week: Continuing to identify services that Case management depends on
Blockers: End of year deliverables

## Slide 5: Status Roundtable – West Virginia
Last week:
This week:
Blockers?:
Notes: Last week: Anticipate reward in next two weeks
This week: Anticipate a reward any moment on procurement, getting the work underway and have project schedule for providing service definitions. Working on identifying a problem that we can solve with Poplin (Opioid-related?).
Blockers: None

## Slide 6: Status Roundtable – WEX Health
Last week:
This week:
Blockers?:
Notes: Last week: Begun looking into finanical management areas.
This week: Internal meetings to go over what this will look like. Will send schedule mid-week.
Blockers?: None, open enrollment taking some resources

## Slide 7: Status Roundtable – Blu Strategies Consulting
Last week: We are working on a data management function taxonomy as the first step that we will bring to the group for review.
This week: I hope to have an update on the development schedule by our next regular poplin group meeting.
Blockers?: None
Notes: Last week:
This week: Develop schedule (Analytics, BI)
Blockers?: None

## Slide 8: Status Roundtable - ONC
Last week:
This week:
Blockers?:
Notes: Last week: Sent comments on MGB submission documents
Next week: Identify folks to embed in the teams, meet next week to discuss
Blockers: Budget reductions

## Slide 9: Functional Area Update
Provider Management (CNSI)
  Screening
  Enrollment
Claims
Pharmacy (MITRE)
Financial Management (WEX Health)
Member Management
  Eligibility (West Virginia)
  Enrollment (Social Interest Solutions?)
Third Party Liability (Henry Chao)
Case Management (Vermont)
  Interaction with Eligibility & Enrollment
Data Warehouse / Business Intelligence / Analytics (Blu Strategies Consulting)
Managed Care Enrollment Broker
Identity Management (Social Interest Solutions?)
Shared Services (MITRE)
  Service registration, service discovery, messaging, security

## Slide 10: EE06: Enroll Provider – Object/Resource Model Diagram
CNSI

## Slide 11: Next week
Release second draft of submission to MGB
Meet with Social Interest Solutions about Poplin involvement
Ongoing work
  Continual progress on functional areas
  Make sure Pivotal Tracker is updated