## Slide 1: Agenda
Status roundtable
Schedule review
CNSI Demo: EE07: Disenroll Provider – Object/Resource Model Diagram
Next week

## Slide 2: Status Roundtable - CNSI
Last week:
This week:
Blockers?:
Epic # | Epic Name | Deliverable | Draft Version - Planned Release Date | Final Version - Planned Release Date | Status | Draft Version - Actual Released Date | Final Version - Actual Released Date
RA-PE - EE05 -01 | EE05:DetermineProviderEligibility - Activity Information Flow | Process Flow (Activity) | 9/29/2017 | 10/13/2017 | 100% | 9/29/2017 | No Change from the Draft Version
RA-PE - EE05 -02 | EE05:DetermineProviderEligibility - Functional Decomposition of Performer | Process Flow (Functions) | 11/3/2017 | 11/17/2017 | 100% | 11/3/2017 | No Change from the Draft Version
RA-PE - EE05 -03 | EE05:DetermineProviderEligibility - Resource Decomposition | Object/Resource Definition | 12/1/2017 | 12/15/2017 | 30% |  | 
RA-PE - EE05 -04 | EE05:DetermineProviderEligibility - Service Specification | API Specification | 12/15/2017 | 12/29/2017 |  |  | 
RA-PE - EE06 -01 | EE06:EnrollProvider - Activity Information Flow | Process Flow (Activity) | 10/6/2017 | 10/20/2017 | 100% | 10/6/2017 | No Change from the Draft Version
RA-PE - EE06 -02 | EE06:EnrollProvider - Functional Decomposition of Performer | Process Flow (Functions) | 11/10/2017 | 11/24/2017 | 75% | 11/9/2017 | 
RA-PE - EE06 -03 | EE06:EnrollProvider - Resource Decomposition | Object/Resource Definition | 12/8/2017 | 12/22/2017 |  |  | 
RA-PE - EE06 -04 | EE06:EnrollProvider - Service Specification | API Specification | 12/22/2017 | 1/5/2018 |  |  | 
RA-PE - EE07 -01 | EE07:DisenrollProvider - Activity Information Flow | Process Flow (Activity) | 10/13/2017 | 10/27/2017 | 100% | 10/13/2017 | No Change from the Draft Version
RA-PE - EE07 -02 | EE07:DisenrollProvider - Functional Decomposition of Performer | Process Flow (Functions) | 11/17/2017 | 12/1/2017 | 75% | 11/17/2017 | 
RA-PE - EE07 -03 | EE07:DisenrollProvider - Resource Decomposition | Object/Resource Definition | 12/15/2017 | 12/29/2017 |  |  | 
RA-PE - EE07 -04 | EE07:DisenrollProvider - Service Specification | API Specification | 12/29/2017 | 1/12/2018 |  |  | 
RA-PE - EE08 -01 | EE08:InquireProviderInformation - Activity Information Flow | Process Flow (Activity) | 10/20/2017 | 11/3/2017 | 100% | 10/20/2017 | No Change from the Draft Version
RA-PE - EE08 -02 | EE08:InquireProviderInformation - Functional Decomposition of Performer | Process Flow (Functions) | 11/24/2017 | 12/8/2017 | 50% |  | 
RA-PE - EE08 -03 | EE08:InquireProviderInformation - Resource Decomposition | Object/Resource Definition | 12/22/2017 | 1/5/2018 |  |  | 
RA-PE - EE08 -04 | EE08:InquireProviderInformation - Service Specification | API Specification | 1/5/2018 | 1/19/2018 |  |  | 
Notes: Last week: Completed disenroll provider object diagrams, working on incquire provider
Next week: Complete object diagrams for EE08, defining objects as part of class diagrams instead of UML – will discuss next week
Blockers: None

## Slide 3: Status Roundtable - MITRE
Last week: Released second draft of guidance document to MITA Governance Board. Developed schedule for security shared service(s). Started development of security share service definition. Completed draft of report for automating MMIS certification using Poplin. Followed up with CA Technologies, Henry Chao. Meeting rescheduled with Social Interest Solutions to discuss deliverable requirements (Enrollment, Identity Management).
This week: Obtain commitments, definitive functional area selections, and schedules from Social Interest Solutions, CA Technologies, Henry Chao. Review report for automating MMIS certification.
Blockers?: None
Notes: Completed business process diagrams for pharmacy, submitted to pharmacy expert and received comments, present at next WG meeting.

## Slide 4: Status Roundtable – Vermont
Last week:
This week:
Blockers?:
Notes: Last week: Continuing to identify services that Case management depends on (80 services+).
This week: Continuing to identify services that Case management depends on
Blockers: Managing conflicting priorities

## Slide 5: Status Roundtable – West Virginia
Last week:
This week:
Blockers?:
Notes: Last week: Awarded contract Monday? Will be able to add resources.
This week:
Blockers: State procurement

## Slide 6: Status Roundtable – WEX Health
Last week:
This week:
Blockers?:
Notes: Last week: Team is reviewing diagrams across FM module, decomposing FM08 and looking to incorporate, formulate schedule
This week: Provide schedule for next meeting and ability to track progress
Blockers?: Getting fully ramped up and getting team’s schedules aligned. Working intenrally.

## Slide 7: Status Roundtable – Blu Strategies Consulting
Last week:
This week:
Blockers?:
Notes: Last week: Continuing to work on data management function. Preliminary dates. Dec 8th for first draft of functional taxonomy. Final on Dec 29th.
This week:
Blockers?: None

## Slide 8: Status Roundtable - ONC
Last week:
This week:
Blockers?:
Notes: Last week: Introduced Al Taylor to the group, he will become the point person, began reviewing guidance document
Next week: review document
Blockers: none

## Slide 9: Poplin Working Group Schedule
Poplin Member | Deliverable | Due Date
MITRE | Report: Automating MMIS Certification Using Poplin | December 5, 2017
Vermont | Case Management: Client/Member Management Service Definition | December 29, 2017
Vermont | Case Management: Service Management Service Definition | December 29, 2017
Vermont | Case Management: Eligibility and Enrollment Service Definition | December 29, 2017
CNSI | Determine Provider Eligibility Service Definition (EE05) | December 29, 2017
CNSI | Enroll Provider Service Definition (EE06) | January 5, 2018
CNSI | Disenroll Provider Service Definition (EE07) | January 12, 2018
CNSI | Inquire Provider Information Service Definition (EE08) | January 19, 2018
MITRE | Poplin reference Implementation v0.2 | January 26, 2018
MITRE | Security Service Definitions - Draft | March 2, 2018
MITRE | Poplin reference Implementation v0.3 | March 30, 2018
West Virginia | Eligibility Service Definitions | TBD
WEX Health | Financial Service Definitions | TBD
Blu Strategies | Data Warehouse / Business Intelligence / Analytics | TBD

## Slide 10: EE07:DisenrollProvider module – Object/Resource Model Diagram
CNSI

## Slide 11: Next week
Cancel/reschedule November 24 meeting?
Object taxonomy meeting Monday, November 20, 2pm
Finalize level of involvement from Social Interest Solutions, CA Technologies.
Ongoing work
  Continual progress on functional areas
  Make sure Pivotal Tracker is updated
Have a great Thanksgiving holiday!