## Slide 1: Agenda
Status roundtable
Schedule review
CNSI Demo: EE06:Provider Enrollment module – Object Specification
And now, a word from our sponsor
Next week

## Slide 2: Status Roundtable - CNSI
Last week:
This week:
Blockers?:
Epic # | Epic Name | Deliverable | Draft Version - Planned Release Date | Final Version - Planned Release Date | Status | Draft Version - Actual Released Date | Final Version - Actual Released Date | Risks/Issues
RA-PE - EE05 -01 | EE05:DetermineProviderEligibility - Activity Information Flow | Process Flow (Activity) | 9/29/2017 | 10/13/2017 | 100% | 9/29/2017 | No Change from the Draft Version | 
RA-PE - EE05 -02 | EE05:DetermineProviderEligibility - Functional Decomposition of Performer | Process Flow (Functions) | 11/3/2017 | 11/17/2017 | 100% | 11/3/2017 | No Change from the Draft Version | 
RA-PE - EE05 -03 | EE05:DetermineProviderEligibility - Resource Decomposition | Object/Resource Definition | 12/1/2017 | 12/15/2017 | 75% | 12/1/2017 |  | Issue: Object Specification Representation tool/repository yet to be finalized by the working group. Mitigation: CNSI uses Class Diagram to represent it
RA-PE - EE05 -04 | EE05:DetermineProviderEligibility - Service Specification | API Specification | 12/15/2017 | 12/29/2017 |  |  |  | 
RA-PE - EE06 -01 | EE06:EnrollProvider - Activity Information Flow | Process Flow (Activity) | 10/6/2017 | 10/20/2017 | 100% | 10/6/2017 | No Change from the Draft Version | 
RA-PE - EE06 -02 | EE06:EnrollProvider - Functional Decomposition of Performer | Process Flow (Functions) | 11/10/2017 | 11/24/2017 | 100% | 11/9/2017 | No Change from the Draft Version | 
RA-PE - EE06 -03 | EE06:EnrollProvider - Resource Decomposition | Object/Resource Definition | 12/8/2017 | 12/22/2017 | 25% |  |  | Issue: Object Specification Representation tool/repository yet to be finalized by the working group. Mitigation: CNSI uses Class Diagram to represent it
RA-PE - EE06 -04 | EE06:EnrollProvider - Service Specification | API Specification | 12/22/2017 | 1/5/2018 |  |  |  | 
RA-PE - EE07 -01 | EE07:DisenrollProvider - Activity Information Flow | Process Flow (Activity) | 10/13/2017 | 10/27/2017 | 100% | 10/13/2017 | No Change from the Draft Version | 
RA-PE - EE07 -02 | EE07:DisenrollProvider - Functional Decomposition of Performer | Process Flow (Functions) | 11/17/2017 | 12/1/2017 | 100% | 11/17/2017 | No Change from the Draft Version | 
RA-PE - EE07 -03 | EE07:DisenrollProvider - Resource Decomposition | Object/Resource Definition | 12/15/2017 | 12/29/2017 | 10% |  |  | Issue: Object Specification Representation tool/repository yet to be finalized by the working group. Mitigation: CNSI uses Class Diagram to represent it
RA-PE - EE07 -04 | EE07:DisenrollProvider - Service Specification | API Specification | 12/29/2017 | 1/12/2018 |  |  |  | 
RA-PE - EE08 -01 | EE08:InquireProviderInformation - Activity Information Flow | Process Flow (Activity) | 10/20/2017 | 11/3/2017 | 100% | 10/20/2017 | No Change from the Draft Version | 
RA-PE - EE08 -02 | EE08:InquireProviderInformation - Functional Decomposition of Performer | Process Flow (Functions) | 11/24/2017 | 12/8/2017 | 75% | 11/24/2017 |  | 
RA-PE - EE08 -03 | EE08:InquireProviderInformation - Resource Decomposition | Object/Resource Definition | 12/22/2017 | 1/5/2018 | 10% |  |  | Issue: Object Specification Representation tool/repository yet to be finalized by the working group. Mitigation: CNSI uses Class Diagram to represent it
RA-PE - EE08 -04 | EE08:InquireProviderInformation - Service Specification | API Specification | 1/5/2018 | 1/19/2018 |  |  |  | 
Notes: Last week: completed activity diagram for the four MITA modules, started looking into object specifications working with class diagrams. Need to address common way to produce object specifications
Next week: Continue to produce object specification for four modules
Blockers: Common way to specify objects

## Slide 3: Status Roundtable - MITRE
Last week: Incorporating Poplin guidance and service definition template into MITA 3.0 Release 2 documents. Reviewed draft of report for automating MMIS certification using Poplin. Following up with Social Interest Solutions and CA Technologies to get commitments.
This week: Release initial draft of new MITA 3.0 Release 2 documents. Present work on automated testing to CMS for approval and wider distribution. Schedule Object Specification Representation tool/repository discussion. Obtain commitments, definitive functional area selections, and schedules from Social Interest Solutions, CA Technologies.
Blockers?: None
Notes: Completed business process diagrams for pharmacy, submitted to pharmacy expert and received comments, present at next WG meeting.

## Slide 4: Status Roundtable – Vermont
Last week:
This week:
Blockers?:
Notes: Last week: Still looking to getting back to work on the documentation. Still working to get wrapped up by year’s end.
This week:
Blockers: Managing conflicting priorities

## Slide 5: Status Roundtable – West Virginia
Last week:
This week:
Blockers?:
Notes: Last week: Contract has been awarded! Key staff rolling in next week.
This week: Identify right resources and start work.
Blockers: None.

## Slide 6: Status Roundtable – WEX Health
Last week:
This week:
Blockers?:
Notes: Last week: Major release made. Darrell and Preston putting together a schedule through mid-Jan. Working through terminology mapping. Identifying big pieces
This week: Working on Billing first. Demo for Dec 8th? High-level flow diagrams. Systems interchange in January.
Blockers?: None

## Slide 7: Status Roundtable – Blu Strategies Consulting
Last week:
This week:
Blockers?:
Notes: Last week: Continuing to work on functional taxonomy aiming for first draft next week.
This week: First draft on taxonomy next week.
Blockers?: None

## Slide 8: Status Roundtable - ONC
Last week:
This week:
Blockers?:
Notes: Last week:
Next week:
Blockers: none

## Slide 9: Poplin Working Group Schedule
Poplin Member | Deliverable | Due Date
MITRE | Report: Automating MMIS Certification Using Poplin | December 5, 2017
Vermont | Case Management: Client/Member Management Service Definition | December 29, 2017
Vermont | Case Management: Service Management Service Definition | December 29, 2017
Vermont | Case Management: Eligibility and Enrollment Service Definition | December 29, 2017
CNSI | Determine Provider Eligibility Service Definition (EE05) | December 29, 2017
CNSI | Enroll Provider Service Definition (EE06) | January 5, 2018
CNSI | Disenroll Provider Service Definition (EE07) | January 12, 2018
CNSI | Inquire Provider Information Service Definition (EE08) | January 19, 2018
MITRE | Poplin reference Implementation v0.2 | January 26, 2018
MITRE | Security Service Definitions - Draft | March 2, 2018
MITRE | Poplin reference Implementation v0.3 | March 30, 2018
West Virginia | Eligibility Service Definitions | TBD
WEX Health | Financial Service Definitions | TBD
Blu Strategies | Data Warehouse / Business Intelligence / Analytics | TBD

## Slide 10: EE06:Provider Enrollment module – Object Specification
CNSI

## Slide 11: And now, a word from our sponsor.
CMS

## Slide 12: Next week
Schedule follow-on object taxonomy meeting
Schedule Object Specification Representation tool/repository.
Finalize level of involvement from Social Interest Solutions, CA Technologies.
Ongoing work
  Continual progress on functional areas
  Make sure Pivotal Tracker is updated