## Slide 1: Agenda
Status roundtable
Schedule review
Poplin Standards Process: A Proposal
Next week

## Slide 2: Status Roundtable - CNSI
Last week:
This week:
Blockers?:
Epic # | Epic Name | Deliverable | Draft Version - Planned Release Date | Final Version - Planned Release Date | Status | Draft Version - Actual Released Date | Final Version - Actual Released Date | Risks/Issues
RA-PE - EE05 -01 | EE05:DetermineProviderEligibility - Activity Information Flow | Process Flow (Activity) | 9/29/2017 | 10/13/2017 | 100% | 9/29/2017 | No Change from the Draft Version | 
RA-PE - EE05 -02 | EE05:DetermineProviderEligibility - Functional Decomposition of Performer | Process Flow (Functions) | 11/3/2017 | 11/17/2017 | 100% | 11/3/2017 | No Change from the Draft Version | 
RA-PE - EE05 -03 | EE05:DetermineProviderEligibility - Resource Decomposition | Object/Resource Definition | 12/1/2017 | 12/15/2017 | 75% | 12/1/2017 |  | Issue: Object Specification Representation tool/repository yet to be finalized by the working group. Mitigation: CNSI uses Class Diagram to represent it
RA-PE - EE05 -04 | EE05:DetermineProviderEligibility - Service Specification | API Specification | 12/15/2017 | 12/29/2017 | 25% |  |  | 
RA-PE - EE06 -01 | EE06:EnrollProvider - Activity Information Flow | Process Flow (Activity) | 10/6/2017 | 10/20/2017 | 100% | 10/6/2017 | No Change from the Draft Version | 
RA-PE - EE06 -02 | EE06:EnrollProvider - Functional Decomposition of Performer | Process Flow (Functions) | 11/10/2017 | 11/24/2017 | 100% | 11/9/2017 | No Change from the Draft Version | 
RA-PE - EE06 -03 | EE06:EnrollProvider - Resource Decomposition | Object/Resource Definition | 12/8/2017 | 12/22/2017 | 75% | 12/1/2017 |  | Issue: Object Specification Representation tool/repository yet to be finalized by the working group. Mitigation: CNSI uses Class Diagram to represent it
RA-PE - EE06 -04 | EE06:EnrollProvider - Service Specification | API Specification | 12/22/2017 | 1/5/2018 |  |  |  | 
RA-PE - EE07 -01 | EE07:DisenrollProvider - Activity Information Flow | Process Flow (Activity) | 10/13/2017 | 10/27/2017 | 100% | 10/13/2017 | No Change from the Draft Version | 
RA-PE - EE07 -02 | EE07:DisenrollProvider - Functional Decomposition of Performer | Process Flow (Functions) | 11/17/2017 | 12/1/2017 | 100% | 11/17/2017 | No Change from the Draft Version | 
RA-PE - EE07 -03 | EE07:DisenrollProvider - Resource Decomposition | Object/Resource Definition | 12/15/2017 | 12/29/2017 | 75% | 12/1/2017 |  | Issue: Object Specification Representation tool/repository yet to be finalized by the working group. Mitigation: CNSI uses Class Diagram to represent it
RA-PE - EE07 -04 | EE07:DisenrollProvider - Service Specification | API Specification | 12/29/2017 | 1/12/2018 |  |  |  | 
RA-PE - EE08 -01 | EE08:InquireProviderInformation - Activity Information Flow | Process Flow (Activity) | 10/20/2017 | 11/3/2017 | 100% | 10/20/2017 | No Change from the Draft Version | 
RA-PE - EE08 -02 | EE08:InquireProviderInformation - Functional Decomposition of Performer | Process Flow (Functions) | 11/24/2017 | 12/8/2017 | 75% | 11/24/2017 |  | 
RA-PE - EE08 -03 | EE08:InquireProviderInformation - Resource Decomposition | Object/Resource Definition | 12/22/2017 | 1/5/2018 | 75% | 12/1/2017 |  | Issue: Object Specification Representation tool/repository yet to be finalized by the working group. Mitigation: CNSI uses Class Diagram to represent it
RA-PE - EE08 -04 | EE08:InquireProviderInformation - Service Specification | API Specification | 1/5/2018 | 1/19/2018 |  |  |  | 
Notes: Last week: completed activity diagram for the four MITA modules, started looking into object specifications working with class diagrams. Need to address common way to produce object specifications
Next week: Continue to produce object specification for four modules
Blockers: Common way to specify objects

## Slide 3: Status Roundtable - MITRE
Last week: Submitted draft of Poplin additions to MITA 3.0 Release 2 documents to MITA Governance Board. Conducted Poplin object representation tool discussion. Met with CAQH (Council for Affordable Quality Healthcare) to discuss potential collaboration with Poplin. Scheduled meetings with Social Interest Solutions and HealthTech Solutions (HTS). Continuing to progress on the Pharmacy and Security service definitions.
This week: Conduct follow-up meetings on object taxonomy and object representation tools. Meet with Social Interest Solutions, HTS on joining Poplin. Schedule meeting with CSRA. Obtain commitments, definitive functional area selections, and schedules from CA Technologies, CAQH.
Blockers?: None
Notes: Completed business process diagrams for pharmacy, submitted to pharmacy expert and received comments, present at next WG meeting.

## Slide 4: Status Roundtable – Vermont
Last week:
This week:
Blockers?:
Notes: Last week: Still looking to getting back to work on the documentation. Still working to get wrapped up by year’s end.
This week:
Blockers: Managing conflicting priorities

## Slide 5: Status Roundtable – West Virginia
Last week:
This week:
Blockers?:
Notes: Last week: Contract has been awarded! Key staff rolling in next week.
This week: Identify right resources and start work.
Blockers: None.

## Slide 6: Status Roundtable – WEX Health
Last week:
This week:
Blockers?:
Notes: Last week: Major release made. Darrell and Preston putting together a schedule through mid-Jan. Working through terminology mapping. Identifying big pieces
This week: Working on Billing first. Demo for Dec 8th? High-level flow diagrams. Systems interchange in January.
Blockers?: None

## Slide 7: Status Roundtable – Blu Strategies Consulting
Last week:
This week:
Blockers?:
Notes: Last week: Continuing to work on functional taxonomy aiming for first draft next week.
This week: First draft on taxonomy next week.
Blockers?: None

## Slide 8: Status Roundtable - ONC
Last week:
This week:
Blockers?:
Notes: Last week:
Next week:
Blockers: none

## Slide 9: Poplin Working Group Schedule
Poplin Member | Deliverable | Due Date
MITRE | Report: Automating MMIS Certification Using Poplin | December 5, 2017
Vermont | Case Management: Client/Member Management Service Definition | December 29, 2017
Vermont | Case Management: Service Management Service Definition | December 29, 2017
Vermont | Case Management: Eligibility and Enrollment Service Definition | December 29, 2017
CNSI | Provider Management: Determine Provider Eligibility Service Definition (EE05) | December 29, 2017
CNSI | Provider Management: Enroll Provider Service Definition (EE06) | January 5, 2018
CNSI | Provider Management: Disenroll Provider Service Definition (EE07) | January 12, 2018
WEX Health | Financial Management: Member Billing Service Definition | January 15, 2018
WEX Health | Financial Management: Member Payment Service Definition | January 15, 2018
WEX Health | Financial Management: State Plan Remittance Service Definition | January 15, 2018
CNSI | Provider Management: Inquire Provider Information Service Definition (EE08) | January 19, 2018
MITRE | Poplin reference Implementation v0.2 | January 26, 2018
MITRE | Security Service Definitions - Draft | March 2, 2018
MITRE | Poplin reference Implementation v0.3 | March 30, 2018
West Virginia | Eligibility Service Definitions | TBD
Blu Strategies | Data Warehouse / Business Intelligence / Analytics | TBD

## Slide 10: Poplin Standards Process: A Proposal

## Slide 11: Poplin Standards Process Goals
Fair
Repeatable
100% consensus on process
Reviewable
Consistent with Poplin goals and principles
Results in service definitions that become standards
  Broad adoption
  Increasing maturity over time

## Slide 12: Poplin Standards Process Steps
Step 1 - Poplin Service Definition Proposal
  Working group member creates service definition
  Discussed and reviewed by Poplin Working Group
  Build consensus and vote (for, against, abstentions)
    100%, 80%, 75%, 50% majority to accept?
Step 2 - Poplin Service Definition Draft
  Publish on GitHub and socialize for comment
  Integrate changes
  Build consensus and vote
    100%, 80%, 75%, 50% majority to accept?

## Slide 13: Poplin Standards Process Steps (continued)
Step 3 - Poplin Service Definition Implementation
  Existence of at least one implementation service definition
  Integrate feedback into service definition
  Build consensus and vote
    100%, 80%, 75%, 50% majority to accept?
Step 4 - Poplin Service Definition Standard
  Review success of implementations and service definition
  Build consensus and vote on service definition becoming Poplin standard
    100%, 80%, 75%, 50% majority to accept?
Appeals
  Must be submitted within three weeks of the decision
  Appealer presents their case, working group votes

## Slide 14: Member Responsibilities
Read the drafts & contribute
Don’t be shy (but do not come on too strong)
Talk with (not just to) people
Treat everyone with respect, even if you disagree
Look for common ground
Don’t settle for second-rate discussion or technology

## Slide 15: Current Members (8)
Blu Strategies Consulting
CMS
CNSI
MITRE
ONC
Vermont
West Virginia
WEX Health
One Vote Per Organization
Each organization must designate a voting member

## Slide 16: Next week
Holiday meeting schedule (12/22, 12/29)
Follow-up discussion on Object Specification Representation tool/repository (12/18)
Follow-up discussion on Object Taxonomy (12/18)
Meeting with HealthTech Solutions (HTS – 12/18), Social Interest Solutions (12/20)
Schedule meeting with CSRA about joining Poplin
Finalize level of commitment from CA Technologies, CAQH
Ongoing work
  Continual progress on functional areas
  Make sure Pivotal Tracker is updated