## Slide 1: Agenda
Status roundtable
Schedule review
Upcoming conferences
Data Standards and Analytics Taxonomy Approach
Poplin Standards Process
SysML/UML Tool Survey
Next week

## Slide 2: Status Roundtable - CNSI
Last week: Working on product release, back January 22
This week: Working on product release, back January 22
Blockers?: Common way to specify objects
Notes: Last week: completed activity diagram for the four MITA modules, started looking into object specifications working with class diagrams. Need to address common way to produce object specifications
Next week: Continue to produce object specification for four modules
Blockers: Common way to specify objects

## Slide 3: Status Roundtable - MITRE
Last week:
  Met with CSRA on joining Poplin effort.
  Investigated Trust Exchange Framework impact on Security shared service.
  Discussed potential collaboration on MESC demonstration with MITA-TAC group.
  Continued to look for a good object representation tool chain solution.
  Followed up with pending members.
  Object specifications for Pharmacy module continue to be refined.
This week:
  Find definitive object representation tool chain for approval.
  Side meeting to discuss potential Poplin demonstration use case.
  Vote next Poplin meeting for approval process for service definitions for Poplin Working Group.
  Obtain commitments, definitive functional area selections, and schedules from pending members.
  Complete Pharmacy object specifications and present at next Poplin meeting.
Blockers?: None

## Slide 4: Status Roundtable – Vermont
Last week:
This week:
Blockers?:
Notes: Last week: Getting back into the work. Bulk is on object definitions – somewhat of a challenge. Lots or partial standards. Don’t completely cover case management (many deal more directly with care management).
This week: Continuing to define objects this week.
Blockers: Managing conflicting priorities

## Slide 5: Status Roundtable – West Virginia
Last week:
This week:
Blockers?:
Notes: Last week: We are still finalizing the staffing structure and complete the onboarding of the new resources.
This week: Once we get that completed in the next couple weeks, we will be able spend a bit more time on defining the use cases. We will have a better update from Jan 26th onwards.
Blockers: None.

## Slide 6: Status Roundtable – WEX Health
Last week:
This week:
Blockers?:
Notes: Last week: Cathcing up after vacation. Working on specifications for items shared last time to add carriers and members to the system. Have some documentation to share on specifications.
This week: Continue to work on specifications.
Blockers?: None

## Slide 7: Status Roundtable – Blu Strategies Consulting
Last week:
This week:
Blockers?:
Notes: Last week: Presenting taxonomy approach today.
This week: Adjustments from meeting and put it out for everyone’s review.
Blockers?: None

## Slide 8: Status Roundtable - ONC
Last week:
This week:
Blockers?:
Notes: Last week: Met on object taxonomy. Focus on clinical terminology
Next week:
Blockers: none

## Slide 9: Poplin Working Group Schedule
Poplin Member | Deliverable | Due Date
CNSI | Provider Management: Determine Provider Eligibility Service Definition (EE05) | December 29, 2017
CNSI | Provider Management: Enroll Provider Service Definition (EE06) | January 5, 2018
CNSI | Provider Management: Disenroll Provider Service Definition (EE07) | January 12, 2018
Blu Strategies | Analytics Taxonomy Draft Proposal | January 12, 2018
WEX Health | Financial Management: Member Billing Service Definition | January 15, 2018
WEX Health | Financial Management: Member Payment Service Definition | January 15, 2018
WEX Health | Financial Management: State Plan Remittance Service Definition | January 15, 2018
MITRE | Object Representation Tool Proposal | January 19, 2018
CNSI | Provider Management: Inquire Provider Information Service Definition (EE08) | January 19, 2018
Vermont | Case Management: Client/Member Management Service Definition | January 26, 2018
Vermont | Case Management: Service Management Service Definition | January 26, 2018
Vermont | Case Management: Eligibility and Enrollment Service Definition | January 26, 2018
MITRE | Poplin Reference Implementation v0.2 | January 26, 2018
MITRE | Security Service Definitions - Draft | March 2, 2018
MITRE | Poplin Reference Implementation v0.3 | March 30, 2018
West Virginia | Eligibility Service Definitions | TBD
Blu Strategies | Data Warehouse / Business Intelligence / Analytics | TBD

## Slide 10: Upcoming Conferences
HIMSS
  Las Vegas, NV
  March 5-9, 2018
  Face-to-face gathering
HIT Connect
  Baltimore, MD
  April 5-6, 2018
  Poplin presentation
  Face-to-face gathering
MESC
  Portland, OR
  August 13-16, 2018
  Poplin demonstration / presentation
  Face-to-face gathering

## Slide 11: Data Standards and Analytics Taxonomy Approach
Blu Strategies Consulting

## Slide 12: Poplin Standards Approval Process

## Slide 13: Poplin Standards Process Steps
Step 1 - Poplin Service Definition Proposal
  Working group member creates service definition
  Discussed and reviewed by Poplin Working Group
  Build consensus and vote (for, against, abstentions)
    67% super-majority to accept
Step 2 - Poplin Service Definition Draft
  Publish on GitHub and socialize for comment
  Integrate changes
  Build consensus and vote
    75% super-majority to accept

## Slide 14: Poplin Standards Process Steps (continued)
Step 3 - Poplin Service Definition Implementation
  Existence of at least one implementation service definition
  Integrate feedback into service definition
  Build consensus and vote
    80% super-majority to accept
Step 4 - Poplin Service Definition Standard
  Review success of implementations and service definition
  Build consensus and vote on service definition becoming Poplin standard
    85% super-majority to accept
Appeals
  Must be submitted within two weeks of the decision
  Appealer presents their case, working group votes

## Slide 15: SysML/UML Tool Survey

## Slide 16: Backup Slides

## Slide 17: Poplin Standards Process: A Proposal

## Slide 18: Poplin Standards Process Goals
Fair
Repeatable
100% consensus on process
Reviewable
Consistent with Poplin goals and principles
Results in service definitions that become standards
  Broad adoption
  Increasing maturity over time

## Slide 19: Member Responsibilities
Read the drafts & contribute
Don’t be shy (but do not come on too strong)
Talk with (not just to) people
Treat everyone with respect, even if you disagree
Look for common ground
Don’t settle for second-rate discussion or technology

## Slide 20: Current Members (8)
Blu Strategies Consulting
CMS
CNSI
MITRE
ONC
Vermont
West Virginia
WEX Health
One Vote Per Organization
Each organization must designate a voting member