## Slide 1: Agenda
Status roundtable
Schedule review
Poplin Standards Process Vote
SysML/UML Tool Survey
Next week

## Slide 2: Status Roundtable - CNSI
Last week: Working on product release, back January 22
This week: Working on product release, back January 22
Blockers?: Common way to specify objects
Notes: Last week: completed activity diagram for the four MITA modules, started looking into object specifications working with class diagrams. Need to address common way to produce object specifications
Next week: Continue to produce object specification for four modules
Blockers: Common way to specify objects

## Slide 3: Status Roundtable - MITRE
Last week:
  KRM Associates will be joining Poplin!
  Continuing to investigate Trust Exchange Framework impact on Poplin.
  Continued discussions with MITA-TAC group on potential MESC demo.
  Continued to look for a good object representation tool chain solution.
  Object specifications for Pharmacy module in review.
This week:
  Side meeting to discuss potential Poplin demonstration use case.
  Obtain commitments, definitive functional area selections, and schedules from pending members.
  Complete Pharmacy object specifications and present at next Poplin meeting.
Blockers?: None

## Slide 4: Status Roundtable – Vermont
Last week:
This week:
Blockers?:
Notes: Last week: Getting back into the work. Bulk is on object definitions – somewhat of a challenge. Lots or partial standards. Don’t completely cover case management (many deal more directly with care management).
This week: Continuing to define objects this week.
Blockers: Managing conflicting priorities

## Slide 5: Status Roundtable – West Virginia
Last week:
This week:
Blockers?:
Notes: Last week: We are still finalizing the staffing structure and complete the onboarding of the new resources.
This week: Once we get that completed in the next couple weeks, we will be able spend a bit more time on defining the use cases. We will have a better update from Jan 26th onwards.
Blockers: None.

## Slide 6: Status Roundtable – WEX Health
Last week:
This week:
Blockers?:
Notes: Last week: Cathcing up after vacation. Working on specifications for items shared last time to add carriers and members to the system. Have some documentation to share on specifications.
This week: Continue to work on specifications.
Blockers?: None

## Slide 7: Status Roundtable – Blu Strategies Consulting
Last week:
This week:
Blockers?:
Notes: Last week: Presenting taxonomy approach today.
This week: Adjustments from meeting and put it out for everyone’s review.
Blockers?: None

## Slide 8: Status Roundtable - ONC
Last week:
This week:
Blockers?:
Notes: Last week: Met on object taxonomy. Focus on clinical terminology
Next week:
Blockers: none

## Slide 9: Poplin Working Group Schedule
Poplin Member | Deliverable | Due Date
CNSI | Provider Management: Determine Provider Eligibility Service Definition (EE05) | December 29, 2017
CNSI | Provider Management: Enroll Provider Service Definition (EE06) | January 5, 2018
CNSI | Provider Management: Disenroll Provider Service Definition (EE07) | January 12, 2018
Blu Strategies | Analytics Taxonomy Draft Proposal | January 12, 2018
WEX Health | Financial Management: Member Billing Service Definition | January 15, 2018
WEX Health | Financial Management: Member Payment Service Definition | January 15, 2018
WEX Health | Financial Management: State Plan Remittance Service Definition | January 15, 2018
MITRE | Object Representation Tool Proposal | January 19, 2018
CNSI | Provider Management: Inquire Provider Information Service Definition (EE08) | January 19, 2018
Vermont | Case Management: Client/Member Management Service Definition | January 26, 2018
Vermont | Case Management: Service Management Service Definition | January 26, 2018
Vermont | Case Management: Eligibility and Enrollment Service Definition | January 26, 2018
MITRE | Poplin Reference Implementation v0.2 | January 26, 2018
MITRE | Security Service Definitions - Draft | March 2, 2018
MITRE | Poplin Reference Implementation v0.3 | March 30, 2018
West Virginia | Eligibility Service Definitions | TBD
Blu Strategies | Data Warehouse / Business Intelligence / Analytics | TBD

## Slide 10: Poplin Standards Approval Process

## Slide 11: Poplin Standards Process Steps
Step 1 - Poplin Service Definition Proposal
  Working group member creates service definition
  Discussed and reviewed by Poplin Working Group
  Build consensus and vote (for, against, abstentions)
    67% super-majority to accept
Step 2 - Poplin Service Definition Draft
  Publish on GitHub and socialize for comment
  Integrate changes
  Build consensus and vote
    75% super-majority to accept
Quorum Requirement: 67%

## Slide 12: Poplin Standards Process Steps (continued)
Step 3 - Poplin Service Definition Implementation
  Existence of at least one implementation service definition
  Integrate feedback into service definition
  Build consensus and vote
    80% super-majority to accept
Step 4 - Poplin Service Definition Standard
  Review success of implementations and service definition
  Build consensus and vote on service definition becoming Poplin standard
    85% super-majority to accept
Appeals
  Must be submitted within two weeks of the decision
  Appealer presents their case, working group votes
Quorum Requirement: 67%

## Slide 13: Vote on Poplin Standards Approval Process
Organization | Representative | Vote
Blu Strategies Consulting |  | 
CMS |  | 
CNSI |  | 
MITRE |  | 
ONC |  | 
Vermont |  | 
West Virginia |  | 
WEX Health |  | 
One Vote Per Organization
Each organization must designate a voting member

## Slide 14: Standard Object Representation Tools

## Slide 15
Two choices
  Focus on exchange formats rather than tools
    Members have flexibility to do work in familiar tools
    Must go with lowest common denominator (e.g. pure UML 2.x)
  All members do Poplin work using open source tool
    Modelio
      Plug-in architecture for additional capabilities (e.g. SysML)

## Slide 16: Backup Slides

## Slide 17: Poplin Standards Process: A Proposal

## Slide 18: Poplin Standards Process Goals
Fair
Repeatable
100% consensus on process
Reviewable
Consistent with Poplin goals and principles
Results in service definitions that become standards
  Broad adoption
  Increasing maturity over time

## Slide 19: Member Responsibilities
Read the drafts & contribute
Don’t be shy (but do not come on too strong)
Talk with (not just to) people
Treat everyone with respect, even if you disagree
Look for common ground
Don’t settle for second-rate discussion or technology