## Slide 1: Agenda
Welcome New Members
Status roundtable
Schedule review
Poplin Standards Process Vote Update
Functional Area Review
Update on Pharmacy Functional Area
Open Discussion

## Slide 2: Welcome New Members!
KRM Associates
Social Interest Solutions
HealthTech Solutions (HTS)

## Slide 3: Status Roundtable - CNSI
Last week: Unable to participate at the moment
This week: Unable to participate at the moment
Blockers?: Competing activities
Notes: Last week: completed activity diagram for the four MITA modules, started looking into object specifications working with class diagrams. Need to address common way to produce object specifications
Next week: Continue to produce object specification for four modules
Blockers: Common way to specify objects

## Slide 4: Status Roundtable - MITRE
Last week:
  Worked with ONC to schedule session on the ONC Trust Exchange Framework.
  Continued discussions with MITA-TAC group and WV on potential MESC 2018 demo.
  Researched existing software solutions for the Security shared service in Poplin, including business process models and object models used by Heart Working Group, Blue Button, and Argonauts.
  Continued to refine the object specifications for Pharmacy module.
This week:
  Side meeting on ONC Trust Exchange Framework
  More discussions to nail down Poplin demonstration use case for MESC 2018 and incorporate feedback.
  Complete business process models, object models for security shared service.
  Complete Pharmacy object specifications and present at next Poplin meeting.
  Obtain commitments, definitive functional area selections, and schedules from pending members.
Blockers?: None

## Slide 5: Status Roundtable – Vermont
Last week: Working on draft for next week, messaging standards, messaging queues, working with Swagger to define APIs (ran into limit with free version).
This week: Working to complete draft next week
Blockers?: Competing priorities, Swagger API limit on free version

## Slide 6: Status Roundtable – West Virginia
Last week: Fraud prevention use case, finalized work flow, comparing with existing system.
This week: Dig more into details and develop service defintioins
Blockers?: None

## Slide 7: Status Roundtable – WEX Health
Last week: Continue service definitions, refinements on member billing from last week’s demonstration, continued service specification for payment services
This week: Continue payment services sevice specification
Blockers?: Competing priorities

## Slide 8: Status Roundtable – Blu Strategies
Last week: Finished taxonomy and on GitHub for review, started digging into TMSIS, decision certification checklist
This week: Continue digging
Blockers?: None

## Slide 9: Status Roundtable - ONC
Last week:
This week:
Blockers?:

## Slide 10: Poplin Working Group Schedule
Poplin Member | Deliverable | Due Date
WEX Health | Financial Management: Member Billing Service Definition | January 26, 2018
WEX Health | Financial Management: Member Payment Service Definition | February 9, 2018
WEX Health | Financial Management: State Plan Remittance Service Definition | February 9, 2018
Vermont | Case Management: Client/Member Management Service Definition | February 9, 2018
Vermont | Case Management: Service Management Service Definition | February 9, 2018
Vermont | Case Management: Eligibility and Enrollment Service Definition | February 9, 2018
MITRE | Poplin Reference Implementation v0.2 | February 23, 2018
MITRE | Security Shared Service Definitions - Draft | March 2, 2018
MITRE | Poplin Reference Implementation v0.3 | March 30, 2018
Blu Strategies | Data Warehouse / Business Intelligence / Analytics Service Definitions | Pending analytic taxonomy strategy approval
West Virginia | Eligibility Service Definitions | TBD
CNSI | Provider Management: Determine Provider Eligibility Service Definition (EE05) | TBD
CNSI | Provider Management: Enroll Provider Service Definition (EE06) | TBD
CNSI | Provider Management: Disenroll Provider Service Definition (EE07) | TBD
CNSI | Provider Management: Inquire Provider Information Service Definition (EE08) | TBD

## Slide 11: Poplin Standards Approval Process
Passed by unanimous vote!

## Slide 12: Functional Areas Divide and Conquer Approach
Provider Management (CNSI)
  Screening
  Enrollment (CNSI)
Claims
Pharmacy (MITRE)
Financial Management (WEX Health)
Member Management
  Eligibility (West Virginia, SIS?)
  Enrollment (SIS?)
Third Party Liability
Case Management (Vermont)
  Interaction with Eligibility & Enrollment
Data Warehouse / Business Intelligence / Analytics (Blu Strategies, HTS?, SIS?)
Identity Management
Managed Care Enrollment Broker
Shared Services (MITRE)
  Service registration, service discovery, messaging, security
Service definitions
actively being
developed today

## Slide 13: Pharmacy Services
MITRE

## Slide 14: Wrap Up
Review documents on Analytics Taxonomy and provide feedback
  https://github.com/MITA-Governance-Board/Poplin/tree/master/service_definitions/analytics
  Vote for Step 1 approval at February 16th meeting for wider distribution (Step 2).
Review documents on Member Billing and provide feedback
  https://github.com/MITA-Governance-Board/Poplin/tree/master/service_definitions/financial_management
  Vote for Step 1 approval at March 2nd meeting for wider distribution (Step 2).
Review documents on Case Management and provide feedback
  https://github.com/MITA-Governance-Board/Poplin/tree/master/service_definitions/case_management
  Vote for Step 1 approval at March 9th meeting for wider distribution (Step 2).

## Slide 15
I seem to be have been disconnected and can’t get back on.
Please review the documents on GitHub and provide feedback.
Also, we should consider for larger modules like pharmacy whether we should have a separate document for each service with a parent document providing the overview or whether it should all be included in one document. Give that some thought and we’ll discuss at a future meeting.
Thanks! Have a great week!

## Slide 16: Backup Slides

## Slide 17: Poplin Standards Process: A Proposal

## Slide 18: Poplin Standards Process Steps
Step 1 - Poplin Service Definition Proposal
  Working group member creates service definition
  Discussed and reviewed by Poplin Working Group
  Build consensus and vote (for, against, abstentions)
    67% super-majority to accept
Step 2 - Poplin Service Definition Draft
  Publish on GitHub and socialize for comment
  Integrate changes
  Build consensus and vote
    75% super-majority to accept
Quorum Requirement: 2/3

## Slide 19: Poplin Standards Process Steps (continued)
Step 3 - Poplin Service Definition Implementation
  Existence of at least one implementation service definition
  Integrate feedback into service definition
  Build consensus and vote
    80% super-majority to accept
Step 4 - Poplin Service Definition Standard
  Review success of implementations and service definition
  Build consensus and vote on service definition becoming Poplin standard
    85% super-majority to accept
Appeals
  Must be submitted within two weeks of the decision
  Appealer presents their case, working group votes
Quorum Requirement: 2/3

## Slide 20: Poplin Standards Process Goals
Fair
Repeatable
100% consensus on process
Reviewable
Consistent with Poplin goals and principles
Results in service definitions that become standards
  Broad adoption
  Increasing maturity over time

## Slide 21: Member Responsibilities
Read the drafts & contribute
Don’t be shy (but do not come on too strong)
Talk with (not just to) people
Treat everyone with respect, even if you disagree
Look for common ground
Don’t settle for second-rate discussion or technology