## Slide 1: Agenda
Roll call
Status roundtable
Functional Area Review
Schedule review
OAuth2 and OpenID Connect
Open Discussion

## Slide 2: Roll Call
Member | Present?
Blu Strategies Consulting | Yes
CMS | No
CNSI | No
CSRA | Yes
HealthTech Solutions | Yes
KRM Associates | Yes
MITRE | Yes
ONC | No
Social Interest Solutions | Yes
Vermont | Yes
West Virginia | No
WEX Health | No

## Slide 3: Status Roundtable - MITRE
Last week:
  Seema Verma at HIMSS presented on the importance of APIs.
  Security shared service definition in MITRE-internal review.
  Met with WV to discuss specifics on use case development for MESC.
  Met with Optum, Ohio about joining Poplin Working Group.
  Followed up with CAQH, CA Technologies on Poplin membership.
This week:
  Complete service definition draft for security shared service.
  Reference implementation v0.2.
  Meet with Magellan about Poplin Working Group
  Obtain commitments, definitive functional area selections, and schedules from pending members.
Blockers: None

## Slide 4: Status Roundtable – Vermont
Last week: Finalizing object definitions.
This week: Adding MITA business processes and completing object work
Blockers: None

## Slide 5: Status Roundtable – West Virginia
Last week:
This week:
Blockers:

## Slide 6: Status Roundtable – WEX Health
Last week: Traveling all week
This week: Update member billing service definition with feedback
Blockers: None

## Slide 7: Status Roundtable – Blu Strategies
Last week: Met with SIS and HealthTech Solutions to integrate feedback and discuss Data Service Taxonomy.
This week: Update Service Taxonomy document with discussion outcomes and reconvene.
Blockers: None

## Slide 8: Status Roundtable - KRM Associates
Last week: Still analyzing the process and the legislation around third party liability.
This week: Begin reaching out to various stakeholders with questions.
Blockers: None

## Slide 9: Status Roundtable – HealthTech Solutions
Last week: We met with BluStrategies and SIS to discuss Data Service Taxonomy document
This week: Meet with the group again for further document discussions
Blockers: None

## Slide 10: Status Roundtable – Social Interest Solutions
Last week: Sent comments to Blu Strategies
This week: Mini-call with other analytics members, work breakdown of analytics architecture
Blockers: None

## Slide 11: Status Roundtable - CSRA
Last week: still getting organized
This week:
Blockers:

## Slide 12: Functional Areas Divide and Conquer Approach
Functional Area | Covered | Member
Provider Management: Screening | OPEN | 
Enrollment |  | CNSI
Claims | OPEN * | * CSRA to help break into subareas
Pharmacy |  | MITRE
Financial Management |  | WEX Health
Member Management: Eligibility |  | West Virginia
Enrollment | OPEN | 
Third Party Liability |  | KRM Associates
Case Management |  | Vermont
Data Warehouse / Business Intelligence / Analytics |  | Blu Strategies, Social Interest Solutions, HealthTech Solutions
Identity Management |  | CSRA
Managed Care Enrollment Broker | OPEN | 
Shared Services: Messaging, Registration/Discovery, Security |  | MITRE

## Slide 13: Poplin Working Group Schedule
Poplin Member | Deliverable | Due Date
WEX Health | Financial Management: State Plan Remittance Service Definition | March 2, 2018
MITRE | Security Shared Service Definitions - Draft | March 9, 2018
West Virginia | Eligibility Service Definitions - Draft | March 16, 2018
Blu Strategies, Social Interest, HealthTech | Data Service Taxonomy – Final Candidate | March 23, 2018
Vermont | Case Management: Client/Member Management Service Definition Draft | March 30, 2018
Vermont | Case Management: Service Management Service Definition Draft | March 30, 2018
Vermont | Case Management: Eligibility and Enrollment Service Definition Draft | March 30, 2018
MITRE | Poplin Reference Implementation v0.3 | March 30, 2018
Blu Strategies, Social Interest, HealthTech | Data Warehouse / Business Intelligence / Analytics Service Definitions | Pending analytic taxonomy strategy approval
KRM Associates | Third Party Liability Service Definitions – Draft | TBD
CSRA | Identity Management Service Definitions - Draft | TBD
CNSI | Provider Enrollment Service Definitions - Draft | TBD

## Slide 14: Upcoming Votes
Like to have discussion for each of these started on GitHub issue tracker
  https://github.com/MITA-Governance-Board/Poplin/issues
Review documents on Data Service Taxonomy and provide feedback
  https://github.com/MITA-Governance-Board/Poplin/tree/master/service_definitions/analytics
  Vote for Step 1 approval at March 23 meeting for wider distribution (Step 2).

## Slide 15: OAuth2 and OpenID Connect
MITRE

## Slide 16: Open Discussion