## Slide 1: Agenda
Roll call
Status roundtable
Functional Area Review
Schedule review
Open Discussion

## Slide 2: Roll Call
Member | Present?
Blu Strategies Consulting | No
CMS | No
CSRA | Yes
HealthTech Solutions | No
KRM Associates | No
MITRE | Yes
ONC | No
Social Interest Solutions | Yes
Vermont | Yes
West Virginia | No
WEX Health | No

## Slide 3: Status Roundtable - MITRE
Last week:
  Presented Poplin to Private Sector Task Group (PSTG)
  Met with Magellan, CAQH about joining Poplin Working Group
  Met with MTA on potential collaborations with Poplin
  More security service definition reviews
  Drafted project plan for use case development for MESC for review by CMS
  CA Technologies to provide decision on joining Poplin mid-April
This week:
  Continue discussions with MTA
  Further reviews of service definition draft for security shared service
  Present draft project plan for approval
Blockers: None

## Slide 4: Status Roundtable – Vermont
Last week: Continued work on the API structure.
This week: Have been getting feedback from others in the state that have case and care efforts going on. Planning on finalizing the API structure next week.
Blockers: None

## Slide 5: Status Roundtable – West Virginia
Last week: We have run into some bandwidth issues due to urgent SOWs that we have received.
This week: We hope to remediate the issue and let you know soon.
Blockers: Urgent SOWs

## Slide 6: Status Roundtable – WEX Health
Last week:
This week:
Blockers:

## Slide 7: Status Roundtable – Blu Strategies
Last week: Updated Data Services Taxonomy with feedback and sent to the team for review.
This week: Facilitate small workgroup session to review new comments. Based on amount of feedback, update and vote Friday.
Blockers: None

## Slide 8: Status Roundtable - KRM Associates
Last week:
This week:
Blockers:

## Slide 9: Status Roundtable – HealthTech Solutions
Last week: Reviewing updated Data Service Taxonomy Document to provide feedback
This week: Small workgroup session to review new comments and prepare document for approval
Blockers: None

## Slide 10: Status Roundtable – Social Interest Solutions
Last week: Reviewed new data service taxonomy document.
This week: Small workgroup session to review new comments and prepare document for approval
Blockers: None

## Slide 11: Status Roundtable - CSRA
Last week:
This week:
Blockers:

## Slide 12: Functional Areas Divide and Conquer Approach
Functional Area | Covered | Member
Provider Management: Screening | OPEN | 
Enrollment |  | CNSI
Claims | OPEN * | * CSRA to help break into subareas
Pharmacy |  | MITRE
Financial Management |  | WEX Health
Member Management: Eligibility |  | West Virginia
Enrollment | OPEN | 
Third Party Liability |  | KRM Associates
Case Management |  | Vermont
Data Warehouse / Business Intelligence / Analytics |  | Blu Strategies, Social Interest Solutions, HealthTech Solutions
Identity Management |  | CSRA
Managed Care Enrollment Broker | OPEN | 
Shared Services: Messaging, Registration/Discovery, Security |  | MITRE

## Slide 13: Poplin Working Group Schedule
Poplin Member | Deliverable | Due Date
WEX Health | Financial Management: State Plan Remittance Service Definition | March 2, 2018
West Virginia | Eligibility Service Definitions - Draft | March 16, 2018
Blu Strategies, Social Interest, HealthTech | Data Service Taxonomy – Final Candidate | March 30, 2018
Vermont | Case Management: Client/Member Management Service Definition Draft | April 27, 2018
Vermont | Case Management: Service Management Service Definition Draft | April 27, 2018
Vermont | Case Management: Eligibility and Enrollment Service Definition Draft | April 27, 2018
Blu Strategies, Social Interest, HealthTech | Data Warehouse / Business Intelligence / Analytics Service Definitions | Pending analytic taxonomy strategy approval
KRM Associates | Third Party Liability Service Definitions – Draft | TBD
CSRA | Identity Management Service Definitions - Draft | TBD

## Slide 14: Upcoming Votes
Like to have discussion for each of these started on GitHub issue tracker
  https://github.com/MITA-Governance-Board/Poplin/issues
Review documents on Data Service Taxonomy and provide feedback
  https://github.com/MITA-Governance-Board/Poplin/tree/master/service_definitions/analytics
  Vote for Step 1 approval at March 30 meeting for wider distribution (Step 2).

## Slide 15: Open Discussion