## Slide 1: Agenda
Welcome CAQH, HMS!
Roll call
Status roundtable
Functional Area Review
Schedule review
Challenges for Poplin
  Which modules to implement first?
Claims Work Breakdown – Coherence, Wily Fox, General Dynamics IT
Address quality
Open discussion

## Slide 2: Roll Call
Member | Present?
Blu Strategies Consulting | No
CAQH | Yes
Coherence | No
CMS | No
General Dynamics IT | Yes
HealthTech Solutions | No
HMS | Yes
Magellan | Yes
MITRE | YEs
MTA | No
Social Interest Solutions | Yes
Vermont | Yes
West Virginia | No
Wily Fox | No

## Slide 3: Status Roundtable – General Project MITRE
Last week:
  CAQH, HMS joined Poplin!
  Continued to build MITRE team
    Software engineers, FHIR expert, summer interns
  Conversations about setting up object repository for Poplin project
This week:
  Follow-up meeting with EHR-LLC about joining Poplin
  Meeting to discuss object repository for Poplin project
    Web site, hosting, etc.
Blockers:
  None

## Slide 4: Status Roundtable – Member Eligibility / Demo West Virginia, MITRE
Last week:
  Met to discuss eligibility use case implementation logistics
    API layer on top of WV legacy eligibility system running in sandbox
  Will focus on fraud detection portion of member eligibility API first
  Started wireframes for interstate interoperability/eligibility use case client app
  Continued to build MITRE development team
This week:
  Develop work breakdown and plan
  Continue development and review of UX mock-ups for eligibility use case
Blockers:
  None

## Slide 5: Status Roundtable – ThreadBear Test Tool / Demo MITRE
Last week:
  Running basic MECT checklist tests in ThreadBear
  Started wireframes for interstate interoperability/eligibility use case client app
  UX kickoff for ThreadBear tool
  Continued to build MITRE team
This week:
  Continue development and review of UX mock-ups for ThreadBear
Blockers:
  None

## Slide 6: Status Roundtable – Case Management Vermont
Last week:
  Updating operational activities to be covered by the case API
This week:
  Update resource definitions to support the operational activities
Blockers:
  Time

## Slide 7: Status Roundtable – Data Services Blu Strategies, Social Interest Solutions, HealthTech Solutions
Last week:
  Kicked off weekly data services meetings
This week:
  Team members to determine #1, #2, #3 choices from areas in Data Services Taxonomy document to tackle
  Determine initial assignments on data services work breakdown.
  Draft of data warehouse architecture
Blockers:
  None

## Slide 8: Status Roundtable – Claims Coherence, Wily Fox, General Dynamics IT
Last week:
  Made progress with collaboration on finalizing the Claims Adjudication Matrix into logical services
  Initial allocation of Claims Adjudication :
    GDIT working on the Provider Service for Claims.
    Wily Fox working on receipt, initial validation (SNIP, etc.), claim history service
This week:
  Target to get some initial inputs from teams and potentially schedule active collaboration for initial validation around consistency and content resolution
Blockers:
  None

## Slide 9: Status Roundtable – Pharmacy Magellan, MITRE
Last week:
  Magellan held a kick off and scoping meeting.
  We crafted an outline of what resources we will be addressing first and received an updated documentation template.
This week:
  Determine the final list of resources based on the results of our discussion from the kickoff meeting and populate the document template.
Blockers:
  None

## Slide 10: Status Roundtable – Provider Screening General Dynamics IT, CAQH, MITRE
Last week:
  Sent out list of API additions in priority order from easiest to hardest
This week:
  Kick off meeting with General Dynamics IT, CAQH on Provider Screening service definition
Blockers:
  None

## Slide 11: Status Roundtable – Third Party Liability HMS
Last week:
This week:
Blockers:

## Slide 12: Functional Areas Divide and Conquer Approach
Functional Area | Covered | Member
Case Management |  | Vermont
Claims |  | Wily Fox, Coherence, General Dynamics IT
Data Warehouse / Business Intelligence / Analytics |  | Blu Strategies, Social Interest Solutions, HealthTech Solutions
Electronic Visit Verification (EVV) |  | MITRE
Financial Management | HOLD | WEX Health
Member Eligibility |  | West Virginia, MITRE
Pharmacy |  | Magellan, MITRE
Provider Screening |  | General Dynamics IT, CAQH, MITRE
Shared Services: Messaging, Registration/Discovery, Security |  | MITRE
Third Party Liability |  | HMS
Identity Management | OPEN | General Dynamics IT (white paper)
Managed Care Enrollment Broker | OPEN | MTA members have expressed interest
Member Enrollment | OPEN | Social Interest has expressed interest
Provider Enrollment | OPEN | 
12

## Slide 13: Poplin Working Group Schedule
Poplin Member | Deliverable | Due Date
Wily Fox, Coherence, GDIT | Claims work breakdown | DONE
General Dynamics IT | Draft Identity Management White Paper | May 18, 2018
Vermont | Case Management: Client/Member Management Service Definition Draft | May 11, 2018
Vermont | Case Management: Service Management Service Definition Draft | May 11, 2018
Vermont | Case Management: Eligibility and Enrollment Service Definition Draft | May 11, 2018
Blu Strategies, Social Interest, HealthTech | Data Warehouse / Business Intelligence / Analytics work breakdown | May 11, 2018 May 18, 2018
MITRE | ThreadBear Automated Test Tool Initial Demo | May 25, 2018
GDIT, MITRE | Provider Screening Service Definitions - Draft | June 15, 2018
West Virginia, MITRE | Member Eligibility Service Definitions - Draft | June 15, 2018
Magellan, MITRE | Pharmacy Service Definitions - Draft | June 29, 2018
MITRE | Interstate Eligibility Use Case Initial Demo | July 21, 2018
MITRE | ThreadBear Automated Test Tool MESC Demo | August 10, 2018
MITRE | Interstate Eligibility Use Case MESC Demo | August 10, 2018

## Slide 14: Challenges for Poplin
Which modules should be prioritized for implementation?
  Most dynamic and greatest impact
    Real time eligibility
      Everything else gets better with membership
      Good way to identify the patient
        Master-person index
          Often misunderstood
          Way to link 300-plus systems across the agency
            Person A in system A is the same as Person B in system B
            In Vermont, about of these systems affects Medicaid
              Most in support of children’s health
          Would need to be a distributed MPI
            Part of data services
            Considered a phone book
            Reduces security requirements of data in MPI itself
            Other systems would reference patient through MPI
    Provider directory
    Financial modules
    CMS reporting/analytics
    Quality assuance
      Third party liability
      Program integrity
    Service authorization
      Pharmacy benefits
    Data quality (both a philosophy as well as shared service)

## Slide 15: Claims Work Breakdown
Coherence, Wily Fox, General Dynamics IT

## Slide 16: Address Quality

## Slide 17: Open Discussion