## Slide 1: Agenda
Roll call
Status roundtable
Functional Area Review
Schedule review
Challenges for Poplin
  How do legacy systems apply the new APIs?
Claims Work Breakdown – Coherence, Wily Fox, General Dynamics IT
Open discussion

## Slide 2: Roll Call
Member | Present?
Blu Strategies Consulting | No
CAQH | Yes
Coherence | Yes
CMS | No
General Dynamics IT | Yes
HealthTech Solutions | No
HMS | No
Magellan | Yes
MITRE | Yes
MTA | No
Social Interest Solutions | Yes
Vermont | Yes
West Virginia | No
Wily Fox | No

## Slide 3: Status Roundtable – General Project MITRE
Last week:
  Added Dr. Ken Laskey (Provider Screening) to the MITRE team
  Added Collin Fingar (Eligibility Use Case demo) to the MITRE team
  Had meeting with Mark Scrimshire, lead for Blue Button 2.0
This week:
  Follow-up meeting with EHR-LLC about joining Poplin
  Meeting to discuss object repository for Poplin project
    Web site, hosting, etc.
Blockers:
  None

## Slide 4: Status Roundtable – Member Eligibility / Demo West Virginia, MITRE
Last week:
  Developed work breakdown and plan
  Developed functional diagrams and how to map to FHIR resources
  Developed two conceptual wireframes for client app
  Sprint burn-down today
  Continued to build MITRE development team
This week:
  Sprint planning session
  Continue development and refinement of wire frames
  Development of UX prototype
Blockers:
  None

## Slide 5: Status Roundtable – ThreadBear Test Tool / Demo MITRE
Last week:
  Running basic MECT checklist tests in ThreadBear
  Started UX concepts for ThreadBear tool
  Worked on background testing and failure reporting
  Continued to build MITRE team
This week:
  Continue development and review of UX mock-ups for ThreadBear
  Continue development of failure reporting and tests
Blockers:
  None

## Slide 6: Status Roundtable – Case Management Vermont
Last week:
  Finalizing activities to be supported by the API
This week:
  Update the API to cover the additional activities defined
Blockers:
  Resources

## Slide 7: Status Roundtable – Data Services Blu Strategies, Social Interest Solutions, HealthTech Solutions
Last week:
  Continued work on data services work breakdown
  Social Interest Solutions started work on data warehouse architecture
This week:
  Determine initial assignments on data services work breakdown for Blu Strategies and HealthTech Solutions
  Draft of data warehouse architecture
Blockers:
  None

## Slide 8: Status Roundtable – Claims Coherence, Wily Fox, General Dynamics IT
Last week:
  Refinement of the Claims Adjudication/Decomposition matrix and assignments
  Initial allocation of Claims Adjudication :
    GDIT working on the Provider Service for Claims.
    Wily Fox working on receipt, initial validation (SNIP, etc.), claim history service
    Coherence working on the DRG Pricer and the Claims Financial API.
This week:
  Seeking to get initial inputs on the first assignments and plan for collaboration to guide consistency among team members
Blockers:
  Logistics to get a common time for collaboration with reviewers.

## Slide 9: Status Roundtable – Pharmacy Magellan, MITRE
Last week:
  Determined the final list of resources based on the results of our discussion from the kickoff meeting and populate the document template.
This week:
  Building diagram of services that make up Pharmacy area
  Continue to develop Pharmacy service definition.
Blockers:
  None

## Slide 10: Status Roundtable – Provider Screening General Dynamics IT, CAQH, MITRE
Last week:
  Held kickoff meeting with GDIT, CAQH, MITRE, Solutions Guidance Corp
  FHIR and code mappings
This week:
  Develop proposals to split work
  Determine service breakdown and initial assignments of members
  Send example FHIR resources to group
Blockers:
  None

## Slide 11: Status Roundtable – Third Party Liability HMS
Last week:
This week:
Blockers:

## Slide 12: Functional Areas Divide and Conquer Approach
Functional Area | Covered | Member
Case Management |  | Vermont
Claims |  | Wily Fox, Coherence, General Dynamics IT
Data Warehouse / Business Intelligence / Analytics |  | Blu Strategies, Social Interest Solutions, HealthTech Solutions
Electronic Visit Verification (EVV) |  | MITRE
Financial Management | HOLD | WEX Health
Member Eligibility |  | West Virginia, MITRE
Pharmacy |  | Magellan, MITRE
Provider Screening |  | General Dynamics IT, CAQH, MITRE
Shared Services: Messaging, Registration/Discovery, Security |  | MITRE
Third Party Liability |  | HMS
Identity Management | OPEN | General Dynamics IT (white paper)
Managed Care Enrollment Broker | OPEN | MTA members have expressed interest
Member Enrollment | OPEN | Social Interest has expressed interest
Provider Enrollment | OPEN | 
12

## Slide 13: Poplin Working Group Schedule
Poplin Member | Deliverable | Due Date
Vermont | Case Management: Client/Member Management Service Definition Draft | May 11, 2018
Vermont | Case Management: Service Management Service Definition Draft | May 11, 2018
Vermont | Case Management: Eligibility and Enrollment Service Definition Draft | May 11, 2018
General Dynamics IT | Draft Identity Management White Paper | DONE
Blu Strategies, Social Interest, HealthTech | Data Warehouse / Business Intelligence / Analytics work breakdown | May 18, 2018 May 25, 2018
MITRE | ThreadBear Automated Test Tool Initial Demo | May 25, 2018
Wily Fox, Coherence, GDIT | Task list and durations for claims service definition development | May 25, 2018
GDIT, MITRE | Provider Screening Service Definitions - Draft | June 15, 2018
West Virginia, MITRE | Member Eligibility Service Definitions - Draft | June 15, 2018
Magellan, MITRE | Pharmacy Service Definitions - Draft | June 29, 2018
MITRE | Interstate Eligibility Use Case Initial Demo | July 21, 2018
MITRE | ThreadBear Automated Test Tool MESC Demo | August 10, 2018
MITRE | Interstate Eligibility Use Case MESC Demo | August 10, 2018

## Slide 14: Challenges for Poplin
How do legacy systems apply the new APIs?
  Can create a data service than connect to legacy service to provide the new API
    Mainframe eligibility system 30 years old and exports flat files that are consumed by other systems to provide eligibility information throughout the enterprise
      API call to determine if person is eligible
  Standards around API platform
    E.g. RedHat OpenShift, create shell of each API and tie it to old system
  Common architecture for states? .NET, Java?
    Publishing of APIs should be independent of underlying technologies
    More problematic than technology stack is real-time orientation of data
      Why is real-time better?
        Batch-style processing no longer meets needs
        Hard leap from where we are to where we need to be
        Vendors aren’t there either
          States aren’t pushing it
        Create the value proposition
          Something that is centralized, one reference point
          MESC might be a good starting point
            Couple of highlights that talks about MITA direction that Poplin is helping to forge
          How can states embrace Poplin?
            Where will APIs be published?
            Prescribe in RFPs
            How do I make systems Poplin-compatible?
            Have existing module with Poplin API
              Technically someone needs to wire them together
            Shell of APIs can help
              Working with vendors to see what APIs they have today
              Convert existing API to a Poplin APIs
              Or “connector” to allow systems without API to have Poplin API
              API Gateway standard?
                Don’t want to specify a particular product – that would be counterproductive
          Giving guidance to system integrators
          Focus on methods of exchange
          Build a sample API gateway for states to invesigtate
      States will push technology stack to vendors

## Slide 15: Claims Work Breakdown
Coherence, Wily Fox, General Dynamics IT

## Slide 16: Open Discussion