## Slide 1: Agenda
Welcome Dave Walsh, MITA-TAC
Roll call
Status roundtable
Functional Area Review
Schedule review
Challenges for Poplin
  Determining gold sources of data
ThreadBear demo
Business process list / business process objectives
API versioning
Open discussion

## Slide 2: Roll Call
Member | Present?
Blu Strategies Consulting | 
CAQH | 
Coherence | 
CMS | 
General Dynamics IT | 
HealthTech Solutions | 
HMS | 
Magellan | 
MITA-TAC | 
MITRE | 
MTA | 
Social Interest Solutions | 
Vermont | 
West Virginia | 
Wily Fox | 

## Slide 3: Status Roundtable – General Project MITRE
Last week:
  Updated project tasks in Pivotal Tracker
  Follow-up meeting with EHR-LLC about joining Poplin
  Setup weekly meeting schedule for provider screening group
This week:
  Meeting to discuss object repository for Poplin project
    Web site, hosting, etc.
Blockers:
  None

## Slide 4: Status Roundtable – Member Eligibility / Demo West Virginia, MITRE
Last week:
  WV produced rough draft of fraud detection APIs for review
  Completed low-fidelity wireframe concept for client app
  Started development of mock eligibility service to interact with WV system
This week:
  Review and refine fraud detection APIs, incorporating FHIR
  Complete UX workflow diagrams and information architecture
  Identify resources and fields
  Start implementing data models for mock eligibility service
Blockers:
  None

## Slide 5: Status Roundtable – ThreadBear Test Tool / Demo MITRE
Last week:
  Added Mark Bestavros to the ThreadBear team
  Continued development of failure reporting and tests
  Background test execution
  Built quick UI for selecting tests and parameters, reviewing results
This week:
  Continue development and review of UX mock-ups for ThreadBear
  Start development work on adding APIs to Provider Screening Module
Blockers:
  None

## Slide 6: Status Roundtable – Case Management Vermont
Last week:
This week:
Blockers:

## Slide 7: Status Roundtable – Data Services Blu Strategies, Social Interest Solutions, HealthTech Solutions
Last week:
  Initial work breakdown:
    Social Interest Solutions working on data warehouse service definition
    HealthTech Solutions working on data collection and data distribution service definitions
      Started planning for data collection service definition
This week:
  Task lists for data warehouse, data collection, data distribution architecture for Pivotal Tracker
Blockers:
  None

## Slide 8: Status Roundtable – Claims Coherence, Wily Fox, General Dynamics IT
Last week:
  Reviewed Claims Adjudication Decomposition.
This week:
  Begin work on Basic Validation Service
Blockers:
  None

## Slide 9: Status Roundtable – Pharmacy Magellan, MITRE
Last week:
  Magellan will meet with MITRE, Jeff Cook, tomorrow 5/25 to review the current draft of our service definition document and diagram.
This week:
  We will make sure we’re all in agreement as to the direction, and get more specific about the scope of the 6/30 deliverable.
Blockers:
  None

## Slide 10: Status Roundtable – Provider Screening General Dynamics IT, CAQH, MITRE
Last week:
  Scheduled recurring meeting for team
  Sent example FHIR resources to group
This week:
  Develop proposals to split work
  Determine service breakdown and initial assignments of members
  Task lists for data warehouse, data collection, data distribution architecture for Pivotal Tracker
Blockers:
  None

## Slide 11: Status Roundtable – Third Party Liability HMS
Last week:
This week:
Blockers:

## Slide 12: Functional Areas Divide and Conquer Approach
Functional Area | Covered | Member
Case Management |  | Vermont
Claims |  | Wily Fox, Coherence, General Dynamics IT
Data Warehouse / Business Intelligence / Analytics |  | Blu Strategies, Social Interest Solutions, HealthTech Solutions
Electronic Visit Verification (EVV) |  | MITRE
Financial Management | HOLD | WEX Health
Member Eligibility |  | West Virginia, MITRE
Pharmacy |  | Magellan, MITRE
Provider Screening |  | General Dynamics IT, CAQH, MITRE
Shared Services: Messaging, Registration/Discovery, Security |  | MITRE
Third Party Liability |  | HMS
Identity Management | OPEN | General Dynamics IT (white paper)
Managed Care Enrollment Broker | OPEN | MTA members have expressed interest
Member Enrollment | OPEN | Social Interest has expressed interest
Provider Enrollment | OPEN | 
12

## Slide 13: Poplin Working Group Schedule
Poplin Member | Deliverable | Due Date
Blu Strategies, Social Interest, HealthTech | Data Warehouse / Business Intelligence / Analytics work breakdown | DONE
Vermont | Case Management: Client/Member Management Service Definition Draft | May 11, 2018
Vermont | Case Management: Service Management Service Definition Draft | May 11, 2018
Vermont | Case Management: Eligibility and Enrollment Service Definition Draft | May 11, 2018
MITRE | ThreadBear Automated Test Tool Initial Demo | May 25, 2018
Wily Fox | Task list and durations for basic claim validation service definition | May 25, 2018
Wily Fox | Task list and durations for duplicate check service definition | May 25, 2018
Wily Fox | Task list and durations for service frequency limitation check service def. | May 25, 2018
GDIT | Task list and durations for provider validation service definition | May 25, 2018
Coherence | Task list and durations for DRG group service definition | May 25, 2018
Coherence | Task list and durations for claims financial services service definition | May 25, 2018
Social Interest Solutions | Task list and durations for data warehouse service definition | TBD
HealthTech Solutions | Task list and durations for data collection service definition | TBD
HealthTech Solutions | Task list and durations for data distribution service definition | TBD

## Slide 14: Poplin Working Group Schedule (continued)
Poplin Member | Deliverable | Due Date
GDIT, MITRE | Provider Screening Service Definitions - Draft | June 15, 2018
West Virginia, MITRE | Member Eligibility Service Definitions - Draft | June 15, 2018
Magellan, MITRE | Pharmacy Service Definitions - Draft | June 29, 2018
MITRE | Interstate Eligibility Use Case Initial Demo | July 21, 2018
MITRE | ThreadBear Automated Test Tool MESC Demo | August 10, 2018
MITRE | Interstate Eligibility Use Case MESC Demo | August 10, 2018

## Slide 15: Challenges for Poplin
Determining gold sources of data

## Slide 16: ThreadBear demo
MITRE

## Slide 17: Business Process Lists / Business Process Objectives

## Slide 18: Business Process Lists / Business Process Objectives
Proposed change to Service Definition Template
  Business Process List should include Business Process Objectives
  How will Poplin APIs help achieve those objectives?

## Slide 19: API Versioning Proposal
service.example.com/api/v1/resource
Allows new versions of APIs to coexist with older versions of APIs
Maintains compatibility while allowing innovation on new APIs

## Slide 20: Open Discussion