## Slide 1: Advancing the Medicaid IT Enterprise Project
Reference Architecture Working Group – June 30, 2017
CMS ALLIANCE TO MODERNIZE HEALTHCARE

## Slide 2: Agenda
Status roundtable
  What you did last week
  What you will do this week
  Any blockers?
Finalize MES functional areas
Service Definition Template
GitHub
Project tracking
Next week

## Slide 3: Status Roundtable
California
  Last week – had to move
  This week – work #1,#2,#3 priorities
  Blockers? – no blockers
CNSI
  Last week – identifying resources to work on effort
  This week – account access for resources
  Blockers? – no blockers
MITRE
  Last week – worked on task list for shared services portion of RA, setup GitHub and started populating, worked on service definition template
  This week – complete service definition template, complete task list
  Blockers? – no blockers
Vermont
  Last week
  This week
  Blockers?

## Slide 4: Finalize Functional Areas
Provider Management (CNSI #1, CA)
  Screening (MITRE PSM team, VT #2)
  Enrollment
Claims
Pharmacy (MITRE Precert group)
Financial Management
Member Management (VT #2, CNSI #2 [delay])
  Eligibility
  Enrollment
Third Party Liability
Case Management (VT #1)
Data Warehouse / Business Intelligence / Analytics
Managed Care Enrollment Broker (CNSI #3 [delay])
Integration Platform (MITRE RA team)
California - #1, #2, #3?
Vermont - #3?

## Slide 5: Service Definition Template
Business processes and object definitions
  Still underway
Resource definitions
  Example: http://standardhealthrecord.org/shr/
API definitions
  Example Swagger: https://watson-api-explorer.mybluemix.net/apis/alchemy-language-v1#/

## Slide 6: GitHub
https://github.com/MITA-Governance-Board/Reference-Architecture
Please send dwhill@mitre.org all GitHub user names that will need repository access

## Slide 7: Project tracking
Trello
JIRA
Taiga
Others (must be free or free to share and available online)
Send in your vote by next Friday.

## Slide 8: Next week
MITRE is continuing to draft a service definition “template”
Capture schedules for service definition work into project tracking tool
Dave Hill will be out next week on vacation
  Anyone want to prep and run next Friday’s meeting?