## Provider_Ref_Arch_Plan
Epic # | Epic Name | Deliverable | Draft Version - Planned Release Date | Final Version - Planned Release Date | Status | Draft Version - Actual Released Date | Final Version - Actual Released Date
RA-PE - EE05 -01 | EE05:DetermineProviderEligibility - Activity Information Flow | Process Flow (Activity) | 2017-09-29 | 2017-10-13 | 100% | 2017-09-29 | No Change from the Draft Version
RA-PE - EE05 -02 | EE05:DetermineProviderEligibility - Functional Decomposition of Performer | Process Flow (Functions) | 2017-11-03 | 2017-11-17 | 75% | 2017-11-03
RA-PE - EE05 -03 | EE05:DetermineProviderEligibility - Resource Decomposition | Object/Resource Definition | 2017-12-01 | 2017-12-15 | 30%
RA-PE - EE05 -04 | EE05:DetermineProviderEligibility - Service Specification | API Specification | 2017-12-15 | 2017-12-29
RA-PE - EE06 -01 | EE06:EnrollProvider - Activity Information Flow | Process Flow (Activity) | 2017-10-06 | 2017-10-20 | 100% | 2017-10-06 | No Change from the Draft Version
RA-PE - EE06 -02 | EE06:EnrollProvider - Functional Decomposition of Performer | Process Flow (Functions) | 2017-11-10 | 2017-11-24 | 75% | 2017-11-09
RA-PE - EE06 -03 | EE06:EnrollProvider - Resource Decomposition | Object/Resource Definition | 2017-12-08 | 2017-12-22
RA-PE - EE06 -04 | EE06:EnrollProvider - Service Specification | API Specification | 2017-12-22 | 2018-01-05
RA-PE - EE07 -01 | EE07:DisenrollProvider - Activity Information Flow | Process Flow (Activity) | 2017-10-13 | 2017-10-27 | 100% | 2017-10-13 | No Change from the Draft Version
RA-PE - EE07 -02 | EE07:DisenrollProvider - Functional Decomposition of Performer | Process Flow (Functions) | 2017-11-17 | 2017-12-01 | 15%
RA-PE - EE07 -03 | EE07:DisenrollProvider - Resource Decomposition | Object/Resource Definition | 2017-12-15 | 2017-12-29
RA-PE - EE07 -04 | EE07:DisenrollProvider - Service Specification | API Specification | 2017-12-29 | 2018-01-12
RA-PE - EE08 -01 | EE08:InquireProviderInformation - Activity Information Flow | Process Flow (Activity) | 2017-10-20 | 2017-11-03 | 100% | 2017-10-20 | No Change from the Draft Version
RA-PE - EE08 -02 | EE08:InquireProviderInformation - Functional Decomposition of Performer | Process Flow (Functions) | 2017-11-24 | 2017-12-08
RA-PE - EE08 -03 | EE08:InquireProviderInformation - Resource Decomposition | Object/Resource Definition | 2017-12-22 | 2018-01-05
RA-PE - EE08 -04 | EE08:InquireProviderInformation - Service Specification | API Specification | 2018-01-05 | 2018-01-19
RA-PM- PM01 -01 | PM01:ManageProviderInformation - Activity Information Flow | Process Flow (Activity) | 2017-12-29 | 2018-01-12
RA-PM- PM01 -02 | PM01:ManageProviderInformation - Functional Decomposition of Performer | Process Flow (Functions) | 2018-01-19 | 2018-02-02
RA-PM- PM01 -03 | PM01:ManageProviderInformation - Resource Decomposition | Object/Resource Definition | 2018-02-02 | 2018-02-16
RA-PM- PM01 -04 | PM01:ManageProviderInformation - Service Specification | API Specification | 2018-02-16 | 2018-03-02
RA-PM- PM02 -01 | PM02:ManageProviderCommunication - Activity Information Flow | Process Flow (Activity) | 2018-01-05 | 2018-01-19
RA-PM- PM02 -02 | PM02:ManageProviderCommunication - Functional Decomposition of Performer | Process Flow (Functions) | 2018-01-26 | 2018-02-09
RA-PM- PM02 -03 | PM02:ManageProviderCommunication - Resource Decomposition | Object/Resource Definition | 2018-02-09 | 2018-02-23
RA-PM- PM02 -04 | PM02:ManageProviderCommunication - Service Specification | API Specification | 2018-02-23 | 2018-03-09
RA-PM- PM03 -01 | PM03:PerformProviderOutreach - Activity Information Flow | Process Flow (Activity) | 2018-01-12 | 2018-01-26
RA-PM- PM03 -02 | PM03:PerformProviderOutreach - Functional Decomposition of Performer | Process Flow (Functions) | 2018-02-02 | 2018-02-16
RA-PM- PM03 -03 | PM03:PerformProviderOutreach - Resource Decomposition | Object/Resource Definition | 2018-02-16 | 2018-03-02
RA-PM- PM03 -04 | PM03:PerformProviderOutreach - Service Specification | API Specification | 2018-03-02 | 2018-03-16
RA-PM- PM07 -01 | PM07:ManageProviderGrievanceAndAppeal - Activity Information Flow | Process Flow (Activity) | 2018-01-19 | 2018-02-02
RA-PM- PM07 -02 | PM07:ManageProviderGrievanceAndAppeal - Functional Decomposition of Performer | Process Flow (Functions) | 2018-02-09 | 2018-02-23
RA-PM- PM07 -03 | PM07:ManageProviderGrievanceAndAppeal - Resource Decomposition | Object/Resource Definition | 2018-02-23 | 2018-03-09
RA-PM- PM07 -04 | PM07:ManageProviderGrievanceAndAppeal - Service Specification | API Specification | 2018-03-09 | 2018-03-23
RA-PM- PM08 -01 | PM08:TerminateProvider - Activity Information Flow | Process Flow (Activity) | 2018-01-26 | 2018-02-09
RA-PM- PM08 -02 | PM08:TerminateProvider - Functional Decomposition of Performer | Process Flow (Functions) | 2018-02-16 | 2018-03-02
RA-PM- PM08 -03 | PM08:TerminateProvider - Resource Decomposition | Object/Resource Definition | 2018-03-02 | 2018-03-16
RA-PM- PM08 -04 | PM08:TerminateProvider - Service Specification | API Specification | 2018-03-16 | 2018-03-30
Formulas:
Final Version - Planned Release Date = [Draft Version - Planned Release Date]+14